## FAT Report
FAT & Visual Inspection test Electrical Dep. ( Infra - Hub )
| Total | 394 | [14 empty] | http://wa.me/201006757564?text=السلام عليكم %20
Serial | Project | Factory & Supplier | Date | Desc. | Quantity | Status | Report | Major Comments | Reference | po/sap | PO no | Supplier Person | Contact Mob | Location | Consultant | Name | Mob | Email
1 | Abou Oweikal | CairoMatic | 2023-12-18 | Control Panel for Fine Screen ( Intake ) | 2 | Rejected | Hyper Link |  | B40-LE-OUT-0482 | 8700003421 | PO.84.229.3 & PO.84.229.4 | Eng Emad Aziz | 0 100 211 3083 | https://maps.app.goo.gl/V4fo1ZairuVfvqrTA | Misr Consultant | Mohamed Saeed | 0 114 082 5305 | Link
2 | Port Said ( PS1 & PS2) | Schneider Badr 1 | 2023-12-20 | Main Distribution Panel MDP-ES2 (PS2) | 1 | Approved | Hyper Link |  | TD-HAC-IND-0278-05 | 8700003500 | 94.59.2 Adden.01 | Eng Monica | 0 128 217 9149 | https://maps.app.goo.gl/8pXpi87vWTUgzJSSA | Dar El Hanadsa | Ahmed Badawy | 0 106 019 0605 | Link
3 | Abou Oweikal | Schneider Badr 1 | 2023-12-24 | Intake Low Voltag Panel (DP-INT-ADD-BK7) | 1 | Approved | Hyper Link |  | B40-LE-OUT-0399 | 8700003297 | N.A | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/8pXpi87vWTUgzJSSA | Misr Consultant | Mohamed Saeed | 0 114 082 5305 | N.A
4 | North Sinai (Gefgafa) | EL MACO | 2023-12-25 | Oil Transformer 800 KVA 11/0.4 KV/ SEI Suppier | 4 | Approved with comments | Hyper Link |  | attached | 8700007506 | N.A | Hussein Magdy | 0 115 986 5490 | https://maps.app.goo.gl/p1o7rfK4pSSdkJZR6 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
5 | El Hammam PS(1,2) | Schneider Badr 2 | 2023-12-28 | MV VFD (Visual Inspection) | 8 | Approved | Hyper Link |  | HAC-HYD-DOC-502/581 | 8700005096 | N.A | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | N.A | N.A | Link
6 | ASSUIT | ECE (Electro Cable Egypt) | 2023-12-28 | ( 18-30 KV ) MV Cables 3*240 mm2 AL/XLPE/STA/PVC (ECE) | 2526 Meter | Approved | Hyper Link |  | WASS_LTR_HAC_NC_1426 | 8700005440 | PO. 101.56.11 Adden.02 | Ahmed Magdy | 0 100 213 2188 | https://maps.app.goo.gl/CtKFX4VM4jqCMV3b8 | N.A | N.A | N.A | N.A
7 | North Sinai (Gefgafa) | SPEC | 2024-01-03 | PABX (Telephone System) Visual Inspection PS#12 | As per attached | Approved | Hyper Link |  | W.GWINP-HAC-DCE-PS12&13-MSL-0134 | 8700007702 | PO. 308.160.1 | Karim Safwat | 0 101 181 9701 | https://maps.app.goo.gl/S6pKZXFUvo4VUzZi6 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
8 | Intake Mostakbal Misr | Tronics | 2024-01-09 | MATV & PABX ( Telephone System) Visual Inspection | As per attached | Approved with comments | Hyperlink |  | MMI-LE-HAC-HYDRO-00216 & 00217 | 8700007424 8700007426 | PO. 223.160.1 & PO. 223.160.4 | Alaa Talaat | 0 109 888 5422 | https://maps.app.goo.gl/Ta7bXK6LHPYBSN9QA | Hydro | Eslam Samir | 0 111 690 0592 | Link
9 | Intake Mostakbal Misr | Al Tawkol | 2024-01-16 | Lighting Poles Al Tawkol Length 8 Meter | 31 | Rejected | Hyper Link |  | MMI-LE-HAC-HYDRO-00180 | 8600073069 | 8600073069 | Hamdy QC | 0 106 867 4123 | https://maps.app.goo.gl/PW7SN9qGxob4fhJPA | Hydro | Eslam Samir | 0 111 690 0592 | Link
10 | Industrial Zone | ECE (Electro Cable Egypt) | 2024-01-17 | ( 18-30 KV ) MV Cables 3*240 mm2 AL/XLPE/STA/PVC (ECE) | 3094 | Approved | Hyper Link |  | MAT-INFRA-MEP-0104 | 8700007746 | PO.342.56.1 (ECE) | Osama Sakr QC | 0 109 608 2226 | https://maps.app.goo.gl/CtKFX4VM4jqCMV3b8 | CEGMAN | Mohamed Abd El Aleem | 0 106 076 7335 | Link
11 | El Hammam PS(1,2) | EMECO | 2024-01-18 | Cable Routing (tray ,trunk and accessories ) | As per attached | Approved | Hyper Link |  | HAC-HYD-PS1-MAR-0059 | 8600073668 | 8600073668 | Mohamed Nabawy | 0 100 529 4133 | https://maps.app.goo.gl/kHhms4XiXC49nrXE6 | Hydro | N.A | N.A | Link
12 | New Delta 2 | Infinity | 2024-01-21 | Aerosol System for New delta | As per attached | Approved | Hper Link |  | NDPD-HAC-MSL-MECH-0038 | 8700007404 | PO 259-116.1 | Basem Hegazy | 0 109 278 5997 | https://maps.app.goo.gl/W7Fjp9VRa3pfuSku6 | Raouf Darwesh | Mohamed abou El Fatouh | 0 100 715 0725 | Link
9` | Intake Mostakbal Misr | Al Tawkol | 2024-01-23 | Lighting Poles Al Tawkol Length 8 Meter | 31 | approved | Hyper Link | Second Time | MMI-LE-HAC-HYDRO-00180 | 8600073069 | 8600073069 | Hamdy QC | 0 106 867 4123 | https://maps.app.goo.gl/PW7SN9qGxob4fhJPA | Hydro | Eslam Samir | 0 111 690 0592 | Link
13 | Industrial Zone | Capital Guard | 2024-01-24 | CO2 System Fire Fighting from Capital Guard | As per attached | Approved | Hper Link |  | attached | 8700007971 | 342.116.2 | Tamer Fekry | 0 122 219 2168 | https://maps.app.goo.gl/eZCtErxpFhFtLCSDA | CEGMAN | Eslam Salah |  | Link
14 | Industrial Zone | ECM Egypt Cables | 2024-01-28 | ( 18-30 KV ) MV Cables 3*400 mm2 AL/XLPE/STA/PVC (ECM) | 1600 | Approved | Hyper Link |  | MAT-INFRA-MEP-0171-REV00.pdf | 8700007863 | PO.342.56.2 | Ahmed Omran | 0 110 095 7000 | https://maps.app.goo.gl/fQBoNRw8XHL7xLfC7 | CEGMAN | Mohamed Abd El Aleem | 0 106 076 7335 | Link
15 | Toshka Zone.S | EL MACO | 2024-01-30 | Oil transformer 1000 KVA 22/0.4KV / KAF | 1 | Approved | Hyper Link |  | attached | 8700008860 | PO 307.65.2 & Adden.01 | Ahmed Fahim | 0 128 555 0181 | https://maps.app.goo.gl/p1o7rfK4pSSdkJZR6 | Cairo University | Abeer | 0 122 770 9514 | Link
16 | Port Said ( PS1 & PS2) | Schneider Badr 1 | 2024-01-31 | Main Distribution Panel MDP-ES1 (PS1) | 1 | Approved | Hyper Link |  | attached | 8700003500 | 94.59.1 | Eng Monica | 0 128 217 9149 | https://maps.app.goo.gl/8pXpi87vWTUgzJSSA | Dar El Hanadsa | Ahmed Badawy | 0 106 019 0605 | Link
17 | Toshka Zone.S | EL MACO | 2024-02-01 | Oil transformer 12500 KVA 22/11KV /KAF | 1 | Approved | Hyper Link |  | attached | 8700006463 | PO 307.65.2 & Adden.01 | Ahmed Fahim | 0 128 555 0181 | https://maps.app.goo.gl/EQ2CfKyX2LNkJU716 | Cairo University | Khaled Eid | 0 111 023 2407 | Link
18 | North Sinai (Gefgafa) | Unisafe | 2024-02-06 | Fire Alarm System for Gefgafa PS#13 | As per attached | Approved | Hyper Link |  | W.GINP-HAC-PS12&13-MSL-0124 | 8700007903 | PO. 308.160.3 Adden01 | Samar Ghareeb | 0 101 239 7481 | https://maps.app.goo.gl/LxuTsFTKsmHB7heR7 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
19 | Industrial Zone | EMAS | 2024-02-07 | MV Distrbuitor (MVSWGR 06) 22KV 18 Cell | 1 | Approved | Hyper Link | Second Time | W.GIIR-LE-HAC-BCED-0013 | 8700007771 | PO.342.68.1 PO (EMAS) | Mohamed Ali | 0 105 002 3103 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | CEGMAN | Mohamed Abd El Aleem | 0 106 076 7335 | Link
20 | North Sinai (Gefgafa) | Novovent Fans | 2024-02-18 | Fans for PS# 12 & 13 | As per attached | Approved | Hyper Link |  | attached | 8700007464 | PO.308.130.1 | Ahmed Magdy | 0 120 343 1905 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
21 | Intake Mostakbal Misr | UIC (El Sewedy Special Cables) | 2024-02-19 | Fiber Optic Cables Special Cables | 7113 Meter | Approved | Hyper Link |  | attached | 8700007749 | PO. 223.160.6 add.01 | Mina | 0 120 865 6602 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Hydro | Eslam Samir | 0 111 690 0592 | Link
22 | RORO | SIGMA | 2024-02-26 | UPS 40K ABB | 1 | Approved | Hyper Link |  | attached | 8700007286 | N.A | Esam Mohamed | 0 111 650 3743 | https://maps.app.goo.gl/ZeistnrMTQDc7qoNA | Shaker Consultant | Ehab Zaki | 0 100 661 9889 | Link
23 | NACWWTP | GIS | 2024-02-27 | Fire Alarm System for NAC WWTP EATON | As per attached | Approved | Hyper Link |  | attached | 8700007983 | PO. 119.160.1 | Mohamed Tharout | 0 106 003 1348 | https://maps.app.goo.gl/Bc9dp5v6VVtbVgfBA | AAW | Mamdouh Kamal | 0 111 821 5341 | Link
24 | Intake Mostakbal Misr | EL Hammam Fans | 2024-02-28 | Fans for Pump Station Intake Visual Inspection | 6 | Approved | Hyper Link |  | attached | 8700007150 | PO.223.130.1 | Ahmed Eid | 0 128 516 3223 | https://maps.app.goo.gl/RAuAJc2BLsvtmnzs8 | Hydro | Eslam Samir | 0 111 690 0592 | Link
25 | New Delta 2 | KYR Company | 2024-03-03 | Fire Alarm System | As per attached | Approved | Hyper Link |  | attached | 8700006597 | PO. 259.160.1 | Youstina | 0 127 020 0668 | https://maps.app.goo.gl/bsGYcpBL6Ec1EzFQ6 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
26 | Intake Mostakbal Misr | EL Hammam Fans | 2024-03-05 | Fans for Pump Station Intake Visual Inspection | 6 | Approved | Hyper Link |  | attached | 8700007150 | PO.223.130.1 | Ahmed Eid | 0 128 516 3223 | https://maps.app.goo.gl/RAuAJc2BLsvtmnzs8 | Hydro | Eslam Samir | 0 111 690 0592 | Link
27 | RORO | Novovent Fans | 2024-03-10 | Fans from NOVOVENT Visual Inspection | As per attached | Approved | Hyper Link |  | attached | 8700006391 | PO.296.130.1 PO.296.130.2 | Ahmed Magdy | 0 120 343 1905 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | Shaker Consultant | N.A | N.A | Link
28 | Intake Mostakbal Misr | El sewedy EGYTECH (A1) | 2024-03-11 | LV Cables El Sewedy EGYTECH | As per attached | Approved | Hyper Link |  | attached | 8700008426 | PO. 223.56.2 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/w2CaySGvVytYuK349 | Hydro | Eslam Samir | 0 111 690 0592 | Link
29 | Industrial Zone | EGYTRAFO | 2024-03-14 | Dry Transformer Service 50 KVA | 1 | Approved | Hyper Link |  | attached | 8700007818 | PO. 342.65.1 | Hassan Ali | 0 111 770 4436 | https://maps.app.goo.gl/HozA1VRkuroPs6w37 | CEGMAN | Araby Safan | 0 109 149 1593 | Link
30 | Zone.G | Infinity | 2024-03-18 | Aerosol System for Zone-G project Visual Inspection | As per attached | Approved | Hyper Link |  | attached | 8700008154 | PO.339.115.1 | Mahmoud Nour El deen | 0 103 062 5972 | https://maps.app.goo.gl/W7Fjp9VRa3pfuSku6 | Hydro | Saied | 0 101 909 7369 | Link
31 | Industrial Zone | EMAS | 2024-04-15 | MV Distrbuitor MVSWGR 22KV 18 Cell | 3 | Approved | Hyper Link |  | attached | 8700007771 | PO.342.68.1 | Mohamed Ali | 0 105 002 3103 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | CEGMAN | Araby Safan | 0 109 149 1593 | N.A
32 | Intake Mostakbal Misr | Schneider Badr 1 | 2024-03-27 | MVSWGR 11KV 10 Cell | 2 | Approved | Hyper Link |  | attached | 8700005876 | PO. 223.68.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/8pXpi87vWTUgzJSSA | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
33 | Intake Mostakbal Misr | Schneider Badr 1 | 2024-03-28 | MVSWGR 11KV 10 Cell | 2 | Approved | Hyper Link |  | attached | 8700005876 | PO. 223.68.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/8pXpi87vWTUgzJSSA | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
34 | Intake Mostakbal Misr | Schneider (Tricom) | 2024-03-31 | Automation Panel (PLC) at Tricom | 2 Cell | Approved | Hyper Link |  | attached | 8700007507 | PO. 223.107.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/aHKospfVv7apcdWs8 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
35 | El Hammam PS(1,2) | Schneider Badr 2 | 2024-04-01 | MV-SWGR 11KV 22 Cell | 1 | Approved | Hyper Link |  | attached | 8700005095 | PO. 202.68.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | N.A | N.A | Link
36 | Intake Mostakbal Misr | UIC (El Sewedy Special Cables) | 2024-04-02 | Fiber accessories Visual Inspection Special Cables | As per attached | Approved with comments | Hyper link | Need update submittal | attached | 8700007749 | PO. 223.160.6 add.01 | Mina | 0 120 865 6602 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Hydro | Mohamed Samy | 0 100 782 8569 | Link
37 | NACWWTP | MB for Engineering & Trading | 2024-04-03 | PABX ( Telephone System ) Visual Inspection | As per attached | Approved | Hyper link |  | attached | 8700008262 | PO. 119.160.2 | Eng Shimaa Elkady | 0 111 914 5812 | https://maps.app.goo.gl/EkdL6bQeB1apuzid7 | AAW | Mamdouh Kamal | 0 111 821 5341 | Link
38 | North Sinai (Gefgafa) | SPEC | 2024-04-18 | PABX ( Telephone System ) Visual Inspection PS#13 | As per attached | Approved | Hyper link |  | attached | 8700007982 | PO. 308.160.4 Adden01 | Karim Safwat | 0 101 181 9701 | https://maps.app.goo.gl/S6pKZXFUvo4VUzZi6 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
39 | Intake Mostakbal Misr | lectro Power - El Habashy | 2024-04-21 | Straight Busway 5000A length 12 meter | 12 Meter | Approved | Hyper Link |  | attached | 8700008247 | 2024/HAC-2-HCI-223-058-01 | Fares Khaled | 0 110 160 0909 | https://maps.app.goo.gl/i7gCszWecJs1Cn6bA | Hydro | Eslam Samir | 0 111 690 0592 | Link
40 | New Delta 2 | BICC | 2024-04-22 | LV Cables & Wires BICC | As per attached | Approved | Hyper Link |  | attached | 8700007146 | PO-259-56-3 SUP | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm8 | Raouf Darwesh | Ahmed El Ethnawy | 0 100 853 1149 | Link
41 | Industrial Zone | ECE (Electro Cable Egypt) | 2024-04-23 | ( 18-30 KV ) MV Cables 3*240 mm2 AL/XLPE/STA/PVC (ECE) | 10179 | Approved | Hyper link |  | attached | 8700007746 | PO.342.56.1 | Osama Sakr QC | 0 109 608 2226 | https://maps.app.goo.gl/CtKFX4VM4jqCMV3b8 | CEGMAN | Araby Safan | 0 109 149 1593 | Link
42 | Industrial Zone | Novovent Fans | 2024-04-24 | Exhaust Fans for Distrbiuator Visual Inspection | 40 | Approved | Hyper Link |  | attached | 8700007739 | PO.342.130.1 | Ahmed Magdy | 0 120 343 1905 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | CEGMAN | Araby Safan | 0 109 149 1593 | N.A
43 | Intake Mostakbal Misr | BICC | 2024-04-28 | BICC Wires for Intake Mostakbal Misr | As per attached | Approved with comments | Hyper Link | Need Update Data sheet for Wires Weight and Diammeter | attached | 8700007437 | PO. 223.56.1 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm8 | Hydro | Mohamed Samy | 0 100 782 8569 | Link
44 | Intake Mostakbal Misr | Schneider Badr 1 | 2024-04-29 | MDB LV Panel for Intake Mostakbal Misr | 1 | Approved | Hyper Link |  | attached | 8700007318 | PO. 223.59.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/8pXpi87vWTUgzJSSA | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
45 | Intake Mostakbal Misr | Schneider Badr 2 | 2024-04-30 | DB Service LV Panel for Intake Mostakbal Misr | 2 | Approved | Hyper Link |  | attached | 8700007318 | PO. 223.59.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
46 | Maghagha JV | SEGA.M | 2024-05-08 | DB Service LV Panel for 6 Lift station | 24 | Approved with comments | Hyper Link |  | attached | 9600000793 | PO. 218.59.3 | Hany Henry | 0 100 216 2226 | https://maps.app.goo.gl/6TwbXifJWZyDKM456 | N.A | N.A | N.A | Link
47 | Toshka Zone.S | Schneider Badr 2 | 2024-05-09 | MV RMU 22KV | 4 | Rejected | Hyper Link |  | attached | 8700006670 | PO. 307.68.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Cairo University | Hussein Raslan | 0 127 485 6805 | Link
48 | RORO | BIMCO | 2024-05-12 | BMS Field & Controller Devices Visual Inspection | As per attached | Approved | Hyper Link |  | attached | 8700006777 | PO.296.107.1 | Passant El-Nokaly | 0 111 244 3314 | https://maps.app.goo.gl/82mmdXqzeRyC9FkPA | Shaker Consultant | N.A | N.A | Link
49 | Maghagha JV | BICC | 2024-05-13 | LV Cables From BICC | As per attached | Approved | Hyper Link |  | attached | 9600000800 | PO. 218.56.2. Sub | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm8 | N.A | N.A | N.A | Link
50 | Abou Oweikal | CairoMatic | 2024-05-14 | Control Panel for Fine Screen ( Intake ) | 2 | Approved | Hyper Link | Second Time | attached | 8700003421 | N.A | Eng Emad Aziz | 0 100 211 3083 | https://maps.app.goo.gl/V4fo1ZairuVfvqrTA | Misr Consultant | Mohamed Saeed | 0 114 082 5305 | Link
50` | Intake Mostakbal Misr | Schneider / Vienna (Online) | 2024-05-16 | VFD Online Fat With Third Party at Vienna | 4 | Approved | Hyper Link |  | attached | 8700007425 | 223.175.1 | Eslam Emad | 0 101 649 4837 | Online Viaenna | MED | Ahmed El semery | 0 109 0004799 0 100 272 8560 | N.A
51 | Al Ayat Intake - Dahshoor Booster Pump | NESSTRA | 2024-05-19 | Mixer Control Panels NESSTRA & Mixers (16) | 4 | Approved | Hyper Link |  | attached | 8700008327 | PO.329-151-5 | Eng.Shreif Nastra | 0 101 183 9715 | https://maps.app.goo.gl/QU17rKy9F2BuzKsS7 | Enviro | Ebraheem | 0 100 461 5973 | Link
52 | Al Ayat Intake - Dahshoor Booster Pump | Engineering for ElectroMechanical equipment(Sakrgugaw) | 2024-05-20 | Dewatering Control Panel (Sakrgugaw) | 8 | Rejected | Hyper Link | First Time | attached | 8700008173 | PO.329-151-4 | Mohamed Mahdy | 0 122 650 0536 | https://maps.app.goo.gl/jeJScTEbksz2Purx7 | Enviro | Fawzy | 0 122 788 6178 | Link
53 | Intake Mostakbal Misr | EL Hammam Fans | 2024-05-21 | Fans for Pump Station Intake Visual Inspection | 18 | Approved | Hyperlink |  | attached | 8700007150 | PO.223.130.1 | Ahmed Eid | 0 128 516 3223 | https://maps.app.goo.gl/RAuAJc2BLsvtmnzs8 | Hydro | Eslam Samir | 0 111 690 0592 | Link
54 | ASSUIT | TIBA | 2024-05-21 | AHU ( Centeral Air Condition Sys.) Manzalawi Group | 2 | Approved | HyperLink |  | N.A | 8700007511 | 101.131.2 | N.A | N.A | https://maps.app.goo.gl/YZ3yMxGHVZSAX6ar7 | N.A | N.A | N.A | N.A
55 | ASSUIT | EGYFAB | 2024-05-21 | Actuators | 2 | Approved | HyperLink |  | N.A | 8700007964 | N.A | N.A | N.A | N.A | N.A | N.A | N.A | N.A
56 | New Delta 2 | BICC | 2024-05-22 | LV Cables BICC | As per attached | Approved | Hyper Link |  | attached | 8700007146 | PO-259-56-3 SUP | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm8 | Raouf Darwesh | N.A | N.A | Link
57 | Intake Mostakbal Misr | El sewedy EGYTECH (A1) | 2024-05-23 | (12-20 KV) MV Cables 3*240 mm2 CU/XLPE/PVC El Sewedy (EGYTECH) | 1404 Meter | Approved | Hyper Link |  | attached | 8700008426 | PO. 223.56.2 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/w2CaySGvVytYuK349 | Hydro | Eslam Samir | 0 111 690 0592 | Link
58 | Industrial Zone | Unisafe | 2024-05-26 | Fire alarm System Edward | 8 | Approved with comments | Hyperlink | Update Panel At approval | attached | 8700008385 | PO. 342.160.1 | Samar Ghareeb | 0 101 239 7481 | https://maps.app.goo.gl/LxuTsFTKsmHB7heR7 | CEGMAN | N.A | N.A | Link
59 | North Sinai (Gefgafa) | EL BARON Group. | 2024-05-27 | Dewatering Pumps & control Panels | As per attached | Approved with comments | Hyperlink | DSV Warehouse - Al Robaiky | attached | 8700007413 | PO.308.151.2 SUP 1 | Mostafa Mohamed | 0 122 918 9080 | https://maps.app.goo.gl/CFksRfNaSJyPBxB66 | Raouf Darwesh | Mohamed abou El Fatouh | 0 100 715 0725 | Link
60 | Ain Sokhna | Energy Store Electrical Trading & Contracting) | 2024-05-28 | UPS 5K IL Mando (Energy Store) | 1 | Approved with comments | HyperLink | Only UPS & Batteries Later | attachd | 8700008334 | PO.344.64.1 | Asmaa Ahab | 0 115 004 5761 | https://maps.app.goo.gl/mLRRkXbmChhzhw2y5 | ECR (Engineering Consultancy & Research) | Eng Farouk | 0 114 425 5130 | Link
61 | Intake Mostakbal Misr | Schneider Badr 2 | 2024-05-29 | HVAC Panels for Intake Mostkbal Misr | 2 | Rejected | NO Report | Without Report | attached | 8700007318 | PO.223.59.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | N.A
62 | Maghagha JV | SEGA.M | 2024-06-02 | External Lighting Panels for Maghagha JV project | 2 | Approved | Hyperlink | Install Panel Holder | attached | 9600000792 | PO.218.59.4 | Hany Henry | 0 100 216 2226 | https://maps.app.goo.gl/6TwbXifJWZyDKM456 | N.A | N.A | N.A | Link
63 | Industrial Zone | ECM Egypt Cables | 2024-06-03 | LV Cables for Outdoor Lighting 4*25 mm2 +1*25 mm2 | As per attached | Approved | Hyperlink |  | attached | 8700008308 | PO.342.56.3 | Ahmed Omran | 0 110 095 7000 | https://maps.app.goo.gl/fQBoNRw8XHL7xLfC7 | CEGMAN | Araby Safan | 0 109 149 1593 | Link
64 | Port Said ( PS1 & PS2) | Schneider Badr 2 | 2024-06-09 | LV Panels for East Port Said Pump Station (MCP/FP) | 4 | Approved | Hyperlink |  | attached | 8700003500 | PO 94.59.2 & 3 | Eng Monica | 0 128 217 9149 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Dar El Hanadsa | Ahmed Badawy | 0 106 019 0605 | Link
65 | Industrial Zone | EL Babtain | 2024-06-10 | Lighting Poles EL Babtain Lenghth 10 Meter | 450 | Approved with comments | Hyperlink | MTC Certificate from Cairo Unversity | attached | 8600085856 | 8600085856 | Ahmed Abou Zaied | 0 102 237 3707 | https://maps.app.goo.gl/StYiQ9gKPcdJXjw2A | CEGMAN | Araby Safan | 0 109 149 1593 | Link
66 | Industrial Zone | Audio Technology | 2024-06-26 | CCTV from Audio Audio Technology Model:- PELCO IPB-IPB 531.1ER | 16 | Approved | Hyperlink |  | attached | 8700007997 | PO.342.160.2 | Mostafa Atta | 0 102 258 0550 | https://maps.app.goo.gl/N4fhv681KudAG5Eh7 | CEGMAN | N.A | N.A | Link
67 | Al Ayat Intake - Dahshoor Booster Pump | Engineering for ElectroMechanical equipment(Sakrgugaw) | 2024-06-27 | Dewatering Control Panel (Sakrgugaw) | 8 | Approved with comments | Hyperlink | Second Time | attached | 8700008173 | PO.329.151.4 | Mohamed Mahdy | 0 122 650 0536 | https://maps.app.goo.gl/jeJScTEbksz2Purx7 | Enviro | Fawzy | 0 122 788 6178 | Link
68 | Industrial Zone | EMAS | 2024-07-01 | MV Distrbuitor MVSWGR 22KV 18 Cell | 1 | Approved with comments | Hyperlink |  | attached | 8700007771 | PO.342.68.1 | Mohamed Ali | 0 105 002 3103 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | CEGMAN | Araby Safan | 0 109 149 1593 | Link
69 | Toshka Zone.S | Novovent Fans | 2024-07-02 | Fan ( Supply & Exhaust) for Toshka Zone S Project | As per attached | Approved with comments | Hyperlink | Missing PT-100 at 3 Models | attached | 8700008526 | PO.307.130.1 | Ahmed Magdy | 0 120 343 1905 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | Cairo University | Amin M Ghorab | 0 102 345 8381/ 0 114 420 6010 | Link
70 | Intake Mostakbal Misr | MTS Fire Fighting | 2024-07-15 | Fire Fighting System MTS | As per attached | Approved with comments | Hyperlink | Complete Approval & Certificates | attached | 8700007964 | Contract 223.152.2 | Fady Saly | 0 127 459 1588 | https://maps.app.goo.gl/XpK5566eqRfU8p1M8 | Hydro | Mohamed Samy | 0 100 782 8569 | Link
71 | Abou Oweikal | Elsewedy Steel | 2024-07-17 | Sample for Lighting Pole 3 Meter | Sample | Approved | Hyperlink |  | attached | 8700004709 | PO.84.77.1 | Ayman El Sewedy | 0 114 282 1320 | https://maps.app.goo.gl/yMyNtTd8iMK14MLi8 | Misr Consultant | Mohamed Saeed | 0 114 082 5305 | Link
72 | Port Said ( PS1 & PS2) | Ateb | 2024-07-18 | Actuators for Valves | 7 | Approved | Hyperlink |  | attached | 8600022986 | Old Attached | Kareem El Hadidy | 0 122 466 6311 | https://maps.app.goo.gl/Jc2ALrmxwraK6TmW7 | Dar El Hanadsa | Eng /Bahaa Mech | 0 106 437 5286 | Link
73 | Intake Mostakbal Misr | I-network Soluation | 2024-07-21 | Passive & Active package ( Data System) Panduit Model | As per attached | Approved | Hyperlink | Complete different Model Approval | attached | 8700008687 | PO.223.160.5 | Alaa Nasser | 0 128 160 3805 | https://maps.app.goo.gl/PsTizy9NywkXTv1j6 | Hydro | Mohamed Samy | 0 100 782 8569 | Link
74 | El Hammam PS(1,2) | Total Power | 2024-07-22 | LV Panels for El Hammam Project (DB-REG & AYS01 & 02) | 3 Panels | Approved | Hyperlink |  | attached | 8700007324 | PO.202.59.2 | Mohamed Ehab | 0 120 002 7656 | https://maps.app.goo.gl/tPXETrhpUWMrqJgP7 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
75 | Intake Mostakbal Misr | Schneider (Tricom) | 2024-07-24 | Automation Panel (PLC) at Tricom | 3 Cells | Approved | Hyper Link |  | attached | 8700007507 | PO.223.107.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/aHKospfVv7apcdWs8 | Hydro | Mohamed Samy | 0 100 782 8569 | Link
76 | Industrial Zone | Stahl Crane | 2024-07-28 | Over Head Crane Yale (Germany) Stahl 5 Ton (CPVF 50-4) | 1 | approved | HyperLink |  | attached | 8700008879 8700008880 | PO 342.145.1 Stahl (Cranes) | Tarek Sakr | 0 109 868 6342 | https://maps.app.goo.gl/pgHZLy8YL5xw5nXG6 | CEGMAN | Mamdouh | 0 106 814 3803 | Link
77 | Industrial Zone | EMAS | 2024-07-29 | MV Distrbuitor MVSWGR 22KV 18 Cell | 3 | Approved with comments | HyperLink | Opening Cables Entry at MV SWGR | attached | 8700007771 | PO.342.68.1 | Mohamed Ali | 0 105 002 3103 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | CEGMAN | Mohamed Abd El Aleem | 0 106 076 7335 | Link
78 | Intake Mostakbal Misr | Schneider Badr 2 | 2024-07-30 | LV Panels ( DP-PS(2)/DP-Admin(2)/DP-LAY/DP-Guard) | 8 | approved | HyperLink |  | attached | 8700007318 | PO.223.59.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
79 | El Hammam PS(1,2) | Egytrafo | 2024-08-04 | Oil Transformers 1000 KVA 11/0.4 KV | 4 | Approved with comments | Hyperlink |  | attached | 8700004224 | PO.202.65.1 | Mohamed Naiem | 0 111 770 4436 | https://maps.app.goo.gl/M7vCpVhrSfDaThTc7 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
80 | Intake Mostakbal Misr | UIC (El Sewedy Special Cables) | 2024-08-05 | LV Cables for Intake Mostkbal Misr | As per attached | approved | Hyperlink | 7 Remaining Cables | attached | 8700007755 | PO.223.56.3 | Mohamed Fathy | 0 100 164 0088 | https://maps.app.goo.gl/VW5x1vsfSXM4ucnn8 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
81 | Ain Sokhna | Quassi System (ABB-Store) | 2024-08-08 | ABB VFD (ACS880-37-580A) 560KW | 6 | Approved with comments | Hyperlink | adding New Card | attached | 8700008335 | PO.344.175.1 | Adnan Ghazy | 0 10 22623982 | https://maps.google.com/?cid=2450294819901776077&entry=gps&g_st=awb | ECR (Engineering Consultancy & Research) | Eng Farouk | 0 114 425 5130 | Link
82 | Toshka Zone.S | FMTU ( Force MTU Power Sys.) | 2024-08-11 | Diesel Generator FMTU (Gen-Set-FM500) 500KVA | 2 | Approved with comments | Hyperlink |  | attached | 8700007342 | PO.307.66.1 | Riham Raafat | 0 106 157 7557 | https://maps.app.goo.gl/kGKndF9AY3jYWjkE9 | Cairo University | Abeer | 0 122 770 9514 | Link
83 | 1000 Fadan | ECE (Electro Cable Egypt) | 2024-08-12 | ( 18-30 KV ) MV Cables 3*240 mm2 AL/XLPE/STA/PVC (ECE) | 12968 Meter | approved | Hyperlink |  | attached | 8700007836 | PO.208.56.3 | Refaat Samy | 0 100 484 4488 | https://maps.app.goo.gl/wcMHoxmqB74zeAvW7 | Khaled Kandel | Ahmed Salah | 0 110 200 2495 0 122 120 8809 | Link
84 | ASSUIT | MK | 2024-08-14 | Fire Alarm system Simplex | As per attached | Approved | Hyperlink | partial PO | attached | 8700008847 | PO.101.160.3 | Noura Rabea | 0 106 640 5858 | https://maps.app.goo.gl/t1CA5XLWyLBoTFzF7 | SEECO | Fares | 0 100 158 6256 | Link
85 | 1000 Fadan | ECE (Electro Cable Egypt) | 2024-08-18 | LV Cables 3*150+70 mm2 at ECE (Electro Cable Egypt) | 544 Meter | Approved | Hyperlink |  | attached | 8700007836 | PO.208.56.3 | Hesham Fares | 0 109 077 7693 | https://maps.app.goo.gl/BBSFDZ786VzQgQG16 | Khaled Kandel | Ahmed Salah | 0 110 200 2495 0 122 120 8809 | Link
86 | ASSUIT | TIBA | 2024-08-19 | Condensate Unit ( Centeral Air Condition Sys.) Manzalawi Group | 4 | Approved | HyperLink |  | attached | 8700007511 | Waiting | Abd El Hammed | 0 100 108 0238 | https://maps.app.goo.gl/YZ3yMxGHVZSAX6ar7 | SEECO | Abd El Hady Soliman | 0 1221075126 | Link
87 | NACWWTP | GSS | 2024-08-25 | Data System for New adminstriation Waste Water plant | As per attached | Approved | Hyperlink | 1 Cisco Switch | attached | 8700008697 | PO.119.160.4 | Omar Diab | 0 101 905 6453 | https://maps.app.goo.gl/Z7hGscvyzJpSAoJG7 | AAW | Mamdouh Kamal | 0 111 821 5341 | Link
88 | Intake Mostakbal Misr | El sewedy EGYTECH (A3) | 2024-08-26 | 3*50+25 mm2 CU/XLPE/MICA/PVC Cable El Sewedy | 250 Meter | Approved | Hyperlink |  | attached | 8700008426 | PO.223.56.2 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/hGMWPmELQdT6H6GE7 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
89 | Intake Mostakbal Misr | Schneider Badr 2 | 2024-08-28 | Bypass System for MV VFD | 4 | Approved | HyperLink |  | attached | 8700005876 | Missing | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
90 | Industrial Zone | ECE (Electro Cable Egypt) | 2024-09-02 | ( 18-30 KV ) MV Cables 3*240 mm2 AL/XLPE/STA/PVC (ECE) | 41758 | Approved | Hyperlink | PO Closed | attached | 8700007746 | PO.342.56.1 | Refaat Samy | 0 100 484 4488 | https://maps.app.goo.gl/wcMHoxmqB74zeAvW7 | CEGMAN | Mohamed Abd El Aleem | 0 106 076 7335 | Link
91 | New Delta 2 | 3-Brothers | 2024-09-03 | MLTSP LV Panel (MDP) | 1 | Approved with comments | Hyperlink | As built for Ambient Temp | attached | 8700007573 | PO.259.59.1 | Mohamed Mohsen | 0 122 776 9966 | https://maps.app.goo.gl/F1EGqhSnF8dfP9988 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
92 | Industrial Zone | EGYTRAFO | 2024-09-04 | Dry Transformer Service 50 KVA | 7 | Approved | Hyperlink | EMT flexible | attached | 8700007818 | PO.342.65.1 | Mohamed Naiem | 0 111 770 4436 | https://maps.app.goo.gl/HozA1VRkuroPs6w41 | CEGMAN | Mohamed Abd El Aleem | 0 106 076 7335 | Link
93 | Toshka Zone.S | El sewedy EGYTECH (A3) | 2024-09-09 | MV & LV Cables for Toshka Zone S PS# 26 & 30 | As per attached | Approved | HyperLink |  | attached | 8700008522 | PO.307.56.5.Add.1 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/hGMWPmELQdT6H6GE7 | Cairo University | Abeer | 0 122 770 9514 | Link
94 | ASSUIT | TEPCO (Oil Transformer ) | 2024-09-12 | (International transformers) Oil Transformer 300 KV 22/0.4 KV for Kiosk (MATELEC S.A.E) | 2 | Approved | Hyperlink | Still Remaining Kiosk Enclosure | attached | 8700008841 | PO.101.279.4 | Mohamed Mahmoud | 0122 644 5280 | https://maps.app.goo.gl/VgoG9S2jdxDmfVkB8 | SEECO | Fares | 0 100 158 6256 | Link
95 | El Hammam PS(1,2) | AUCOM | 2024-09-16 | Soft Starter (L-MVE-0200-V11-SC31-E3-F1-L1-B1-PF1)#PS1 1050KW & #PS2 780KW | 10 | Approved | Hyperlink | Remaining 06 Soft Starter & power for Heater | attached | 8700005099 | PO.202.321.1 | Bassem | 0 12 27389312 | https://maps.app.goo.gl/vhpBnjFhegv5uRGK7 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
96 | Maghagha JV | RMG | 2024-09-24 | Control system PLC & Instruments | 6 | Approved with comments | Hyperlink | Missing AI Card & Earth Connection | attached | 9600000852 | PO.218.107.3.SUP.1 | Kareem Ashraf | 0 1226526026 | https://maps.app.goo.gl/EWFzHoavYSAstZxQ9 | N.A | N.A | N.A | Link
97 | Meet El Amel | EISAC -EMAS | 2024-09-25 | Maintenance ABB VFD Model:- ACS880-31-105A-3+P940 | 1 | Approved | Hyperlink |  | attached |  | PO.157.59.5.Add.1 | Shady Rabie | 0 12 04941275 | https://maps.app.goo.gl/5bscKL3NpCnfMepW8 | N.A | N.A | N.A | Link
98 | El Hammam PS(1,2) | Schneider Badr 2 | 2024-09-26 | Bypass System for MV VFD | 8 | Approved with comments | HyperLink |  | attached | 8700008841 | PO 101.279.4 PO Kiosk (Tepco) | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
99 | Intake Mostakbal Misr | Schneider Badr 2 | 2024-09-26 | HVAC Panels for Intake Mostkbal Misr | 2 | Approved with comments | Hyperlink | Second Inspection | attached | 8700007318 | PO.223.59.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
100 | ASSUIT | TEPECO (Kiosk ) | 2024-09-29 | Kiosk 300 KV 22/0.4 KV for Kiosk (TEPECO) | 2 | Approved with comments | Hyperlink |  | attached | 8700008841 | PO 101.279.4 PO Kiosk (Tepco) | Mohamed Ebrahim | 0 11 44077333 | https://maps.app.goo.gl/7vwVC37gUGxr2VeC6 | SEECO | Fares | 0 100 158 6256 | Link
101 | Intake Mostakbal Misr | Al Tawkol | 2024-09-30 | Lighting Poles Al Tawkol Length 8 Meter (Regulator) | 8 | approved | Hyperlink |  | attached | 8600073069 | Missing | Hamdy QC | 0 106 867 4123 | https://maps.app.goo.gl/PW7SN9qGxob4fhJPA | Hydro | Mohamed Samy | 0 100 782 8569 | Link
102 | Zone.G | EGYTRAFO | 2024-10-02 | Oil Transformer 50 KVA 22/0.4 KV | 1 | approved | Hyperlink |  | attached | 8700008693 | 339.65.1 | Mohamed Naiem | 0 111 770 4436 | https://maps.app.goo.gl/HozA1VRkuroPs6w41 | Hydro | N.A | N.A | N.A
103 | Intake Mostakbal Misr | Schneider (Tricom) | 2024-10-03 | RTU for Dignals(MVSWGR & MDB & SUB Service & DBVAC) | 1 | approved | Hyperlink |  | attached | 8700007507 | PO.223.107.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/aHKospfVv7apcdWs8 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | N.A
104 | Intake Mostakbal Misr | Schneider (Tricom) | 2024-10-08 | Marshalling Panels - LCP - Main Pumps | 1 | Approved with comments | Hyperlink |  | attached | 8700007318 | Missing | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/aHKospfVv7apcdWs8 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | N.A
105 | Intake Mostakbal Misr | PETRA | 2024-10-13 | HVAC DX Package Units | 2 | Approved | Hyperlink |  | attached | 8700007578 | PO- 223.103.2 PETRA IMM | Ahmed Youssef | 0 11 16977710 | https://maps.app.goo.gl/pNgB3AgWaRVoXpvC6 | Hydro | N.A | N.A | Link
106 | Toshka Zone.S | UIC (El Sewedy Special Cables) | 2024-10-16 | LV Cables & Wires from Elsewedy | As per attached | Approved | Hyperlink |  | attached | 8700008523 | PO. 307.56.4 PO (UIC) | Badr Ahmed | 0 114 982 0636 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Cairo University | Khaled Eid | 0 111 023 2407 | Link
107 | Zone.G | Watania (advanced Sys.) | 2024-10-21 | Booster Pumps Set Model 2 KVE 10/5 T+N ADAC | 1 | Approved | Hyperlink |  | attached | 8700008774 | PO 339.151.2 | Hamdy Zidan Watania | 0 11 54888774 | https://maps.app.goo.gl/JgEVKggLghgAWJNV8 | Hydro | N.A | N.A | N.A
108 | Port Said ( PS1 & PS2) | 3-Brothers | 2024-10-23 | Power Junction Boxes for Pumps (PS#1 & PS#2) | 7 | Approved with comments | Hyperlink | Internal Protective Mirror | attached | 8600093533 | 8600093533 | Mohamed Mohsen | 0 122 776 9966 | https://maps.app.goo.gl/F1EGqhSnF8dfP9988 | Dar El Hanadsa | N.A | N.A | Link
109 | New Delta 2 | Light House | 2024-10-28 | LUX Test Lighting Fixture | Samples | Approved with comments | Hyperlink | Battery Different | attached | 8600071179 | 8600071179 | Shimaa | 0 100 014 6115 | https://maps.app.goo.gl/oM6qm74MzjLEpd6v6 | Raouf Darwesh | Ahmed El Ethnawy | 0 100 853 1149 | Link
110 | Abou Oweikal | Grand Water | 2024-11-04 | Circulation Pump | 1 | Approved | Hyperlink |  | attached | 8700007754 | PO.84.282.4 | Sara Farouk | 0 109 997 0414 | https://maps.app.goo.gl/fiNL16exMeg9VUH9A | Misr Consultant | N.A | N.A | Link
111 | Toshka Zone.S | Schneider Badr 2 | 2024-11-05 | MV RMU 22KV | 4 | Approved with comments | Hyperlink | Re-Inspection Second Time | attached | 8700006670 | PO.307.68.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Cairo University | Khaled Eid | 0 111 023 2407 | Link
112 | ASSUIT | El Mohandes | 2024-11-10 | Generator (Diesel) Emergency 1000KVA | 2 | Approved | Hyperlink |  | attached | 8700007342 | PO.101.66.4 Sup.01 | Mohmed Ali | 0 12 70098379 | https://maps.app.goo.gl/g3PPevxbyry5ALXd8 | SEECO | Fares | 0 100 158 6256 | Link
113 | RORO | UIC (El Sewedy Special Cables) | 2024-11-11 | LV Cables 4*4 mm2 CU/XLPE/STA/PVC for RORO Project | 2059 Meter | Approved | Hyperlink | Remaining Package to delivered | attached | 8600080652 | PO 8600080652 | Mohamed Ibrahim | 0 12 26068563 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Shaker Consultant | Ehab Zaki | 0 100 661 9889 | Link
114 | Intake Mostakbal Misr | GEMKA | 2024-11-13 | Penstocks | 2 | Approved with comments | Hyperlink | Documentation | attached | 8700005509 | PO.223.296.3 | ahmed Soultan | 0 11 52289212 | https://maps.app.goo.gl/7VDKweb4FsGeQeim6 | Hydro | Mohamed Samy | 0 100 782 8569 | Link
115 | Abou Oweikal | El sewedy EGYTECH (A1) | 2024-11-14 | LV Cables EGYTECH | As per attached | Approved | Hyperlink | Replacement for Stolen Cables | B40-LE-OUT-0445 | 8700009021 | PO.84.56.10 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/w2CaySGvVytYuK349 | Misr Consultant | N.A | N.A | N.A
116 | Zone.G | ECE (Electro Cable Egypt) | 2024-11-13 | LV Wires (3 & 4 & 6)mm2 | As per attached | Approved | Hyperlink |  | HAC-HYD-MAR-0268 | 8700008885 | PO.339.56.1 | Hesham Fares | 0 109 077 7693 | https://maps.app.goo.gl/BBSFDZ786VzQgQG16 | HYDRO | N.A | N.A | Link
117 | El Hammam PS(1,2) | AUCOM | 2024-09-17 | Soft Starter (L-MVE-0200-V11-SC31-E3-F1-L1-B1-PF1)#PS1 1050KW & #PS2 780KW | 6 | Approved | Hyperlink |  | attached | 8700005099 | PO.202.321.1 | Bassem | 0 122 738 9312 | https://maps.app.goo.gl/vhpBnjFhegv5uRGK7 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
118 | Industrial Zone | ESC | 2024-09-18 | Booster Pumps (IDEAL BOMBAS) | 5 | Approved | Hyperlink |  | attached | 8700008249 | PO.342.151.1 | Mohamed abd Elnasser | 0 128 781 6955 | https://maps.app.goo.gl/zYcskUYYtLZmpTME6 | CEGMAN | Nabil Mohamed | 0 11 25595914 | Link
119 | Toshka Zone.S | Zaki El Sewedy | 2024-11-20 | LV MDB Panels | 2 | Rejected | NO Report | Without Report | attached | 8700008295 | PO.307.59.1 | Hussein Magdy | 0 115 986 5490 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | Cairo University | Hussein Raslan | 0 127 485 6805 | Link
120 | 6 October tretment Plant | MK | 2024-11-25 | Fire Alarm system ( Control Module (5) & Siren / Strobe (7) ) | As per attached | Approved | Hyperlink |  | attached | 8700004886 | PO.159.160.3 | Noura Rabea | 0 106 640 5858 | https://maps.app.goo.gl/t1CA5XLWyLBoTFzF7 | Enviro | Fawzy Abd El Raouf | 0 122 788 6178 | Link
121 | 6 October tretment Plant | Universe | 2024-11-25 | Thermostat Gewiss GW 10703 for Fans MV Room | 4 | Approved | Hyperlink |  | attached | 8700006125 | PO.159.107.2 | MR. Ahmed Sayed Store | 0 101 785 2916 | https://maps.app.goo.gl/oBvzCJRihxynssj17 | Enviro | Fawzy Abd El Raouf | 0 122 788 6178 | Link
122 | Ain Sokhna | Quassi | 2024-11-25 | Addational Card for VFD (New Request) | 6 | Approved | Hyperlink |  | attached | 8700008335 | PO.344.175.2.adden.01 | Adnan Ghazy | 0 10 22623982 | https://maps.google.com/?cid=2450294819901776077&entry=gps&g_st=awb | ECR (Engineering Consultancy & Research) | Mohamed Amir | 0 10 10048354 | Link
123 | 6 October tretment Plant | Novovent Fans | 2024-11-26 | Fan ( Supply & Exhaust) | 2 | Approved | Hyperlink |  | attached | 8700006375 | PO.159.130.4 | Ahmed Salah | 0 122 299 8517 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | Enviro | Ebraheem | 0 100 461 5973 | Link
124 | Al Ayat Intake - Dahshoor Booster Pump | Novovent Fans | 2024-11-26 | Fan ( Supply & Exhaust) | As per attached | Approved | Hyperlink |  | attached | 8700007910 | PO.329.130.1 | Ahmed Salah | 0 122 299 8517 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | Enviro | Ebraheem | 0 10 04615973 | Link
125 | Assuit | Novovent Fans | 2024-11-26 | Fans FDA BOX 560 & FDA Box 630 | 2 | Approved | Hyperlink |  | attached | 8600040507 8600036784 | 8600040507 8600036784 | Ahmed Salah | 0 122 299 8517 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw8 | SEECO | N.A | N.A | N.A
126 | Sanhour | MK | 2024-11-27 | Fire Alarm system (Appollo) | As per attached | Approved | Hyperlink |  | attached | 8700008741 | PO.317.160.1 | Noura Rabea | 0 106 640 5858 | https://maps.app.goo.gl/t1CA5XLWyLBoTFzF7 | Stantic | Khaled Sayed | 0 11 43491374 | Link
127 | ASSUIT | MK | 2024-11-27 | Remaining Fire alarm System (Simplex) | As per attached | Approved | Hyperlink |  | attached | 8700008847 | PO.101.160.3 | Noura Rabea | 0 106 640 5858 | https://maps.app.goo.gl/t1CA5XLWyLBoTFzF7 | SEECO | Fares | 0 100 158 6256 | N.A
128 | Intake Mostakbal Misr | Schneider (Tricom) | 2024-11-28 | RTU Regulator | 1 | Approved with comments | Hyperlink | Remaining HMI | attached | 8700007507 | PO.223.107.1 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/aHKospfVv7apcdWs8 | Hydro | Eslam Samir Mohamed Samy | 0 111 690 0592 0 100 782 8569 | Link
129 | Industrial Zone | Arabtech | 2024-12-02 | LV Panels MDB & BD for Distrbuitors | 16 | Approved with comments | Hyperlink | Replace DMM to ABB | attached | 8700007998 | PO.342.59.1 | haitham Farag | 0 106 106 5111 | https://maps.app.goo.gl/LGuWcTQigX8Bt3ix5 | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
130 | 6 October tretment Plant | Advanced WareHouse | 2024-12-02 | Pressure Switch | 4 | Approved | Hyperlink |  | attached | 8700006765 | PO.159.107.1 | Mohamoud Nasser | 0 11 11917280 | https://maps.app.goo.gl/iGeZ1tx9mEscqd2X7 | Enviro | Fawzy Abd El Raouf | 0 122 788 6178 | N.A
131 | Intake Mostakbal Misr | EL Hammam Fans | 2024-12-05 | Exaust Fans AIRCOL 150 MP (EF.01) | 17 | Approved with comments | Hyperlink |  | attached | 8700009421 | PO.223.130.2 | Ahmed Eid | 0 128 516 3223 | https://maps.app.goo.gl/RAuAJc2BLsvtmnzs8 | Hydro | Eslam Samir | 0 111 690 0592 | Link
132 | El Hammam PS(1,2) | Schneider (Tricom) | 2024-12-08 | PLC & RTU | 4 | Approved with comments | Hyperlink |  | attached | 8700005098 | PO.202.107.1 | Omar Assem | 0 101 649 4837 | https://maps.app.goo.gl/aHKospfVv7apcdWs8 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
133 | Industrial Zone | SIRAJ | 2024-12-09 | Street Outdoor Lighting 150 Watt ( EGYLUX) | 2853 | Approved | Hyperlink |  | attached | 8700008047 | PO.342.76.1 | Mohamed Attia | 0 12 72411529 | https://maps.app.goo.gl/SYoHjfGtALqaM91b9 | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
134 | North Sinai (Gefgafa) | Novovent Fans | 2024-12-10 | Exhaust & Supply fans for Gefgafa Project PS 12 & 13 | as per attached | Approved | Hyperlink |  | attached | 8700007464 | PO.308.130.1 | Ahmed Salah | 0 122 299 8517 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | Raouf Darwesh | Mohamed abou El Fatouh | 0 100 715 0725 | Link
135 | Port Said ( PS1 & PS2) | BICC | 2024-12-11 | BICC Power Cable 1*500 mm2 Cu/XlPE/PVC | 1189 Meter | Approved | Hyperlink |  | attached | 8700009311 | PO.94.56.4 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm8 | Dar El Hanadsa | N.A | N.A | Link
136 | ASSUIT | MK | 2024-12-12 | Flame Detectors & Mointor Module Fire alarm System | As per attached | Approved | Hyperlink |  | attached | 8700008847 | PO.188.101.3 | Noura Rabea | 0 106 640 5858 | https://maps.app.goo.gl/t1CA5XLWyLBoTFzF7 | SEECO | Amr AbdEl Raouf | N.A | N.A
137 | Ain Sokhna | ABB | 2024-12-16 | LV Panels Boards MDB-400V & MDB-690V | 2 | Approved | Hyperlink |  | attached | 8700008407 | PO.344.59.1 | Marwa Magdy | 0 10 29046555 | https://maps.app.goo.gl/D7ZTAoMwkxga4dBZ6 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 11 12256829 | Link
138 | Industrial Zone | Zaki El Sewedy (Egytrafo) | 2024-12-17 | Only Dry Transformer 50KVA 22/0.4 LV (inside Kiosk ) / EGYTRAFO | 10 | Approved with comments | Hyperlink |  | attached | 8700008773 | PO.342.279.1 | Walaa Mustafaa | 0 107 092 9657 | https://maps.app.goo.gl/HozA1VRkuroPs6w41 | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
139 | Ain Sokhna | El Sewedy (Transformers) | 2024-12-18 | El Sewedy Dry Transformers ( 3500 KVA 22/0.690 KV & 500 KVA 0.690/0.400 KV ) | 2 | Approved | Hyperlink |  | attached | 8700008465 | PO.344.65.1 | Ahmed Awny | 0 109 864 5953 | https://maps.app.goo.gl/ewefwJ1nYefmTEau6 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 11 12256829 | Link
140 | NACWWTP | BICC | 2024-12-22 | BICC LV Power Cables | As per attached | Approved | Hyperlink | P.O Cancelled from BICC | attached | 8700008626 | PO.119.56.2 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | AAW | Mamdouh Kamal | 0 111 821 5341 | Link
141 | Zone.G | Schneider Badr 2 | 2024-12-23 | MV Panels MV SWGR 22KV External Item 01 | 1 | Approved with comments | Hyperlink | Need to close before any packing | attached | 8700008696 | PO.339.68.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
142 | Sanhour | MK | 2024-12-23 | Remaining Fire Alarm system (Beam Detector Fireray -6010-300) | 1 | Approved | Hyperlink |  | attached | 8700008741 | PO.317.160.1 | Noura Rabea | 0 106 640 5858 | https://maps.app.goo.gl/t1CA5XLWyLBoTFzF7 | Stantic | N.A | N.A | N.A
143 | Sanhour | El sewedy EGYTECH (A1) | 2024-12-24 | (12-20 KV) MV Cables 3*240 mm2 AL/XLPE/STA/PVC (EGYTECH) | 967 Meter | Approved | Hyperlink |  | attached | 8700009569 | PO.317.56.1 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/6iaeqPztf8uoVZmb7 | Electricity Company | Mohamed Ali Ali | 0 112 475 9807 | Link
144 | El Hammam PS(1,2) | Capital Guard | 2024-12-26 | Fire Alarm System (Simplex) | As per attached | Approved | Hyperlink | Missing Items | attached | 8700006134 | PO.202.160.1.sup.01 | Ragaa | 0 12 79162000 | https://maps.app.goo.gl/eZCtErxpFhFtLCSDA | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
145 | ASSUIT | Mecorr | 2024-12-28 | Cathodic Transformers |  | Rejected | NO Report | Without Report | attached | 8700001009 | Mecorr Contract | Ashraf Abdel Baseer | 0 106 620 1119 | https://maps.app.goo.gl/sRHTBg95uizRe8fG8 | SEECO | Fares | 0 100 158 6256 | Link
146 | Zone.G | Schneider Badr 2 | 2024-12-29 | LV MDB Board item (6,7,8,9,10,11,12) | 14 | Approved with comments | Hyperlink |  | attached | 8700008694 | PO.339.59.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
147 | Zone.G | Schneider Badr 2 | 2024-12-30 | MV RMU 22KV (RM6) item 4 | 13 | Approved with comments | Hyperlink |  | attached | 8700008696 | PO.339.68.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
148 | Industrial Zone | ECE Egypt Cables | 2024-12-31 | Lighting Street LV Cables 3*3 mm2 Cu/XLPE/PVC | 23234 Meter | Approved | Hyperlink |  | attached | 8700009703 | PO.342.56.4 | Hesham Fares | 0 109 077 7693 | https://maps.app.goo.gl/BBSFDZ786VzQgQG16 | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
149 | Abou Oweikal | MAM for Engineering Industries & Electrical Supplies | 2025-01-02 | Water Hammer system Control Panels (Treated Water Lines) | 2 | Approved | Hyperlink |  | attached | 8700003490 | Contract El Amal | Ahmed El Hamy | 0 111 273 0007 | https://maps.app.goo.gl/zrMojfznkPNkjX9Z7 | Misr Consultant | Qadry | 0 120 003 3934 | Link
150 | Toshka Zone.S | Zaki El Sewedy | 2025-01-06 | LV MDB Panels PS (26&30) Toshka Zone.S | 2 | Rejected | Hyperlink | Re-Inspection | attached | 8700008295 | PO.307.59.1 | Hussein Magdy | 0 115 986 5490 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | Cairo University | Khaled Eid | 0 111 023 2407 | Link
151 | Industrial Zone | Watania (advanced Sys.) | 2025-01-12 | Fire Fighting Pumps (Jockey & Elec & Diesel) | 1 | Approved | Hyperlink | Rejected Jockey & Elec Pump | attached | 8700008250 | PO.342.104.1 | Mohamed Gaber | 0 110 104 2683 | https://maps.app.goo.gl/JgEVKggLghgAWJNV8 | CEGMAN | Ahmed said | 0 106 704 7657 | Link
152 | 6 October tretment Plant | El sewedy EGYTECH (A3) | 2025-01-13 | LV Cables 3*240+120 mm2 | 498 Meter | Approved | Hyperlink |  | attached | 8700009455 | PO.159.56.5.adden.01 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/hGMWPmELQdT6H6GE7 | Enviro | Youssef El Saeedy | 0 10 61598033 | Link
153 | Tahta treatment Plant | KORRA ENERI | 2025-01-15 | Generators for Intake & Treatment Plant 1600 & 1800KVA | 2 | Approved | Hyperlink |  | attached | 8700010395 | PO.192.66.1 | Eslam Hamdy | 0 102 555 6067 | https://maps.app.goo.gl/TwWqJ7HhGVNksACs7 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
154 | RORO | Capital Guard | 2025-01-16 | Fire Alarm System | As per attached | Approved | Hyperlink |  | attached | 8700009621 | PO.296.160.4 | Sara Moustafa | 0 120 236 6091 | https://maps.app.goo.gl/eZCtErxpFhFtLCSDA | Shaker Consultant | N.A | N.A | Link
155 | RORO | Arabtech | 2025-01-19 | LV Panels (LP-OFF&PP-OFF&ELP-OFF&UPP-OFF7EDP-OFF&DB-OFF&UPP-OFF&LP-WS&ELP-WS&ELP-SG) & Bypass UPS Panel | As per attached | Approved With Comments | Hyperlink |  | attached | 8700009402 | PO.296.59.1 | Ahmed Yosrry | 0 10 21115869 | https://maps.app.goo.gl/usAv4xP1q9UcyESe8 | Shaker Consultant | Mohamed El Gazzar | 0 10 05380410 | Link
156 | New Delta 2 | Sakr | 2025-01-22 | Weed Screen Cleaning Machine | As per attached | Approved | Hyperlink |  | attached | 8700007314 | PO.259.296.3 | Moustafa Abd Elrahman | 0 112 126 5124 | https://maps.app.goo.gl/LxfzLWUsKXrJZuTY6 | Raouf Darwesh | Mohamed abou El Fatouh | 0 100 715 0725 | N.A
157 | RORO | BIMCO | 2025-01-22 | RORO BMS (3) LCP System | As per attached | Approved | Hyperlink |  | attached | 8700006777 | PO.296.107.1 | Passant El-Nokaly | 0 111 244 3314 | https://maps.app.goo.gl/82mmdXqzeRyC9FkPA | Shaker Consultant | Abdallah abd El Tawab | 0 10 6324 2374 | Link
158 | RORO | MK | 2025-01-27 | Fire Alarm Panel & Printer & auto Dailer | As per attached | Approved | Hyperlink | 5 Item Need approval (alternative) | attached | 8700009874 | PO.296.160.5 | Noura Rabea | 0 106 640 5858 | https://maps.app.goo.gl/t1CA5XLWyLBoTFzF7 | Shaker Consultant | N.A | N.A | Link
159 | Tahta treatment Plant | Gilla | 2025-01-29 | RMU (3+1 LBS) / 11 KV | 4 | Approved With Comments | Hyperlink | Shunt Trip Coil & SF6 Indicators | attached | 8700009879 | PO.192.68.1 | Mahmoud Salem | 0 106 552 5118 | https://maps.app.goo.gl/zmAGTm3sqgM7h7sb8 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
160 | Tahta treatment Plant | 2B (Hitachi/ABB) | 2025-01-29 | ABB Oil Transformers 1500 KVA 11/0.4 KV | 2 | Approved | Hyperlink |  | attached | 8700009746 | PO.192.65.1 | Ahmed Fathy | 0 109 880 7718 | https://maps.app.goo.gl/VRe3T3wC7MWtNR848 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
161 | ASSUIT | Mecorr | 2025-01-30 | Cathodic Transformers | 2 | Approved | Hyperlink | Second Inspection | attached | 8700001009 | Mecorr Contract | Ashraf Abdel Baseer | 0 106 620 1119 | https://maps.app.goo.gl/sRHTBg95uizRe8fG8 | SEECO | Fares | 0 100 158 6256 | Link
162 | ASSUIT | Powerline | 2025-01-30 | Under Voltage Coil | 6 | Rejected | Hyperlink |  | attached | 8700009671 | PO.339.160.1 | Tamer | 0 10 61179848 | https://maps.app.goo.gl/7Zm4jGbvisu8Gmc2A | SEECO | Fares | 0 100 158 6256 | Link
163 | Zone.G | Schneider Badr 2 | 2025-02-02 | MV SWGR 6.6 KV ( Item 03 ) | 2 | Approved With Comments | Hyperlink |  | attached | 8700008696 | PO.339.68.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
164 | Toshka Zone.S | Zaki El Sewedy | 2025-02-06 | LV MDB Panels PS (26&30) Toshka Zone.S | 2 | Approved With Comments | Hyperlink | Third Inspection | attached | 8700008295 | PO.307.59.1 | Hussein Magdy | 0 115 986 5490 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | Cairo University | Ahmed Esam | 0 111 530 8156 | Link
165 | Ain Sokhna | ICE | 2025-02-04 | Cathodic Protection ICE (Batch 01) | As per attached | Approved | Hyperlink |  | attached | 8700008973 | PO.344.299.1 | Ehab Ayman | 0 100 709 0897 | https://maps.app.goo.gl/WvHTgdAD37p2zqo17 | ECR (Engineering Consultancy & Research) | Mohamed El Saied | 0 105 024 4472 | Link
166 | Zone.G | IFSS | 2025-02-04 | Fire alarm System | As per attached | Approved | Hyperlink |  | attached | 8700009671 | PO.339.160.1 | Wael El Hadary | 0 106 804 5810 | https://maps.app.goo.gl/zeVvkVvPn8SJUzUB9 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
167 | Industrial Zone | Zaki El Sewedy (Egytrafo) | 2025-02-10 | Only Dry Transformer 50KVA 22/0.4 LV (inside Kiosk ) / EGYTRAFO | 6 | Approved | Hyperlink |  | attached | 8700008773 | PO.342.279.1 | Walaa Mustafaa | 0 107 092 9657 | https://maps.app.goo.gl/HozA1VRkuroPs6w41 | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
168 | Industrial Zone | ESC (FGECO) | 2025-02-11 | Local Control Panel for Booster Pumps (IDEAL BOMBAS) | 2 | Rejected | Hyperlink | Thickness Busbar & Trip Unit | attached | 8700008249 | PO.342.151.1 | Mohamed abd Elnasser | 0 128 781 6955 | https://maps.app.goo.gl/QNZDGUdfhJ2JYbwq8 | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
169 | Intake Mostakbal Misr | Watania (advanced Sys.) | 2025-02-12 | Booster Pumps from Watania (DAB) | 1 | Approved | Hyperlink |  | attached | 8700008712 | PO.223.151.2 | Mohamed Gaber | 0 110 104 2683 | https://maps.app.goo.gl/JgEVKggLghgAWJNV8 | Hydro | Eslam Samir | 0 111 690 0592 | Link
170 | Intake Mostakbal Misr | MTS Watania (advanced Sys.) | 2025-02-12 | Fire Pumps LUBI (Jockey & Elec & Diesel) from MTS | 3 | Approved | Hyperlink | Except Jockey DAB Model need approval | attached | 8700007964 | Contract PO.223.152.2 | Fady Saly | 0 127 459 1588 | https://maps.app.goo.gl/JgEVKggLghgAWJNV8 | Hydro | Eslam Samir | 0 111 690 0592 | Link
171 | RORO | BIMCO | 2025-02-13 | RORO BMS (9) LCP System & Server & Workstation | As per attached | Approved | Hyperlink | Except Printer | attached | 8700006777 | PO.296.107.1 | Passant El-Nokaly | 0 111 244 3314 | https://maps.app.goo.gl/82mmdXqzeRyC9FkPA | Shaker Consultant | Mostafa Hassan | 0 111 829 2552 | Link
172 | Tahta treatment Plant | KORRA ENERI | 2025-01-16 | Generators Fuel System (Tanks & Pumps & LCP) & Enclosure 1600 KVA GeN | As per attached | Approved | Hyperlink | Need Ultrasonic Welding Certificate | attached | 8700010395 | P.O 192.66.2 Add.01 P.O 192.66.1 | Eslam Hamdy | 0 102 555 6067 | https://maps.app.goo.gl/TwWqJ7HhGVNksACs7 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
173 | RORO | Planetx | 2025-02-17 | FM2000 System RORO | As per attached | Approved | Hyperlink | (Code.C) Need Approval from Consultant | attached | 8700009893 | PO.296.116.2 | Aya Mohammed | 0 111 687 3272 | https://maps.app.goo.gl/Ri3z8T5bVY3N4LDw5 | Shaker Consultant | N.A | N.A | Link
174 | Ain Sokhna | El sewedy EGYTECH (A3) | 2025-02-18 | MV & LV Cabels El sewedy EGYTECH | As per attached | Approved | Hyperlink |  | attached | 8700009608 | PO.344.56.1 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/hGMWPmELQdT6H6GE7 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 111 225 6829 | Link
175 | Industrial Zone | ROSENBERG | 2025-02-19 | Rosenberg Exhaust Fans | As per attached | Approved | Hyperlink |  | attached | 8700009792 | PO.342.130.2 | Marco Kamal | 0 103 083 9722 | https://maps.app.goo.gl/6rUF5xwtWX5vkvhF9 | CEGMAN | Alaa Abuzied | 0 102 365 4636 | Link
176 | Toshka Zone.S | Zaki El Sewedy | 2025-02-20 | LV MDB Panels PS (26&30) Toshka Zone.S | 2 | Approved | Hyperlink | Fourth Inspection | attached | 8700008295 | PO.307.59.1 | Hussein Magdy | 0 115 986 5490 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | Cairo University | Hussein Raslan | 0 127 485 6805 | Link
177 | North Sinai (Gefgafa) | Misr of Modern Crane | 2025-02-23 | Cranes (Overhead & Gantry& Monrail) Misr of Modern Crane | As per attached | Approved | Hyperlink |  | attached | 8700008873 | PO.308.145.2 | Mohamed Hussein | 0 100 852 0679 | https://maps.app.goo.gl/NKMJCqkjtu4W6gmx8 | Raouf Darwesh | Mohamed abou El Fatouh | 0 100 715 0725 | Link
178 | Sanhour | Novovent Fans | 2025-02-25 | Fans for Sanhour Project | As per attached | Approved | Hyperlink |  | attached | 8700008067 | PO.317.130.1 | Ahmed Salah | 0 122 299 8517 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | Stantic | N.A | N.A | Link
179 | Industrial Zone | Zaki El Sewedy | 2025-02-27 | Kiosk 50 KV 22/0.4 KV for Kiosk (Zaki Elsewedy ) | 8 | Approved with comments | Hyperlink | Shunt Trip Coil | attached | 8700008773 | PO.342.279.1 | Walaa Mustafaa | 0 107 092 9657 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
180 | T.Lines (New Administration Capital) | Giza Cables | 2025-03-03 | (12-20 KV) MV Cables 3*240 mm2 AL/XLPE/STA/PVC (Giza Cables) | 7527 Meter | Approved | Hyperlink |  | attached | 8700009697 | PO.349.56.1 | Hassan Ali | 0 109 711 8883 | https://maps.app.goo.gl/9zAve9EaSS19kRiE8 | ECG | Mohamed abd El Mageed | 0 11 17001711 | Link
180 | T.Lines (New Administration Capital) | Giza Cables | 2025-03-03 | LV Cables for T.Lines (New Administration Capital) | 3300 Meter | Approved | Hyperlink |  | attached | 8700009697 | PO.349.56.1 | Hassan Ali | 0 109 711 8883 | https://maps.app.goo.gl/YiRTzz6HfLJYb5vX6 | ECG | Mohamed abd El Mageed | 0 11 17001711 | Link
181 | Industrial Zone | ESC (FGECO) | 2025-03-05 | Local Control Panel for Booster Pumps (IDEAL BOMBAS) | 2 | Approved | Hyperlink |  | attached | 8700008249 | PO.342.151.1 | Mohamed abd Elnasser | 0 128 781 6955 | https://maps.app.goo.gl/QNZDGUdfhJ2JYbwq8 | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
182 | Toshka Zone.S | SPEC | 2025-03-09 | Telephone & Data System (SPEC) Toshka Zone .S | As per attached | Approved with comments | Hyperlink |  | attached | 8700009955 | PO.307.160.2 | Karim Safwat | 0 101 181 9701 | https://maps.app.goo.gl/S6pKZXFUvo4VUzZi6 | Cairo University | Abeer | 0 122 770 9514 | Link
183 | Toshka Zone.S | El sewedy EGYTECH (A3) | 2025-03-10 | (12-20 KV) MV Cables 3*240 mm2 CU/XLPE/STA/PVC (El Sewedy) | 201 Meter | Approved | Hyperlink |  | attached | 8600105826 8600108416 | 8600105826 8600108416 | Mohamed Ebrahim | 0 12 26068563 | https://maps.app.goo.gl/WZWQP2Dx7cuMz9GF6 | Cairo University | Ahmed Esam | 0 11 15308156 | Link
184 | Maghagha JV | ESC | 2025-03-16 | Maghagha Submersible Sewage Pumps (Al Sheikh zyad main) | 4 | Approved | HyperLink |  | attached | 9600000848 | PO.218.151.4 PO.218.151.5 | Mohamed abd Elnasser | 0 128 781 6955 | https://maps.app.goo.gl/zYcskUYYtLZmpTME6 | N.A | N.A | N.A | N.A
185 | Tahta treatment Plant | Yama Engineering System | 2025-03-18 | Fire Fighting Pumps (Jockey & Elec & Diesel) | As per attached | Approved | Hyperlink |  | attached | 8700009667 | PO.192.204.1 | Mahmoud Hommosy | 0 101 847 2297 | https://maps.app.goo.gl/Sn6xyJfVBZtpfW6f9 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
186 | Tahta treatment Plant | Misr of Modern Crane | 2025-03-19 | Monorails Cranes (Hoist Only) | 9 | Approved | Hyperlink |  | attached | 8700009782 | PO.192.145.1 PO.192.145.2.adden.1 | Mohamed Hussein | 0 100 852 0679 | https://maps.app.goo.gl/rPXX5VZTrfbHX1pb6 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
187 | Tahta treatment Plant | Hydrotech For Engineering & Technical Services | 2025-03-20 | Drainage (Flygt) | 2 | Approved | Hyperlink |  | attached | 8700009688 | PO.192.151.1 | Abd El Rahman | 0 120 464 4955 | https://maps.app.goo.gl/ePxCKJhy8moa1Xub6 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
188 | ASSUIT | Powerline | 2025-03-22 | Under Voltage Coil (Re-Inspection) | 6 | Approved | Hyperlink | Re-Inspection | attached | 8700009671 | PO.339.160.1 | Tamer | 0 10 61179848 | https://maps.app.goo.gl/iysYPhmVzSX7Tyho7 | SEECO | Fares | 0 100 158 6256 | Link
189 | Tahta treatment Plant | IMAG | 2025-03-23 | Service Pump (Booster Skid) | 1 | Approved with comments | Hyperlink |  | attached | 8700009790 | PO.192.151.2 | Fady Saly | 0 127 459 1588 | https://maps.app.goo.gl/1gGEvwfwU2b1aGbbA | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
190 | Intake Mostakbal Misr | lectro Power - El Habashy | 2025-03-24 | Busway 5000A length 26.05 meter | As per attached | Approved | Hyperlink |  | attached | 8700008247 | 2024/HAC-2-HCI-223-058-01 | Fares Khaled | 0 110 160 0909 | https://maps.app.goo.gl/i7gCszWecJs1Cn6bA | Hydro | Eslam Samir | 0 111 690 0592 | Still
191 | Abou Oweikal | El sewedy EGYTECH (A1) | 2025-03-25 | (12-20 KV) MV Cables 3*95 mm2 AL/XLPE/STA/PVC (El Sewedy) | 6439 | Approved | Hyperlink |  | attached | 8700009915 | PO.84.56.12 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/6iaeqPztf8uoVZmb7 | Misr Consultant | N.A | N.A | Link
192 | Ain Sokhna | PETRA | 2025-03-26 | AC Package Unit | 1 | Approved | Hyperlink |  | attached | 8700009451 | PO.344.131.1 | Ahmed Youssef | 0 11 16977710 | https://maps.app.goo.gl/C5cwST5SS7be5bHcA | ECR (Engineering Consultancy & Research) | Mohamed El Saied | 0 105 024 4472 | Link
193 | Ain Sokhna | ABB | 2025-03-26 | PLC System (2 panels ) | 2 | Approved with comments | Hyperlink |  | attached | 8700009458 | PO.344.107.1 | Yasser Hamza | 0 100 605 5248 | https://maps.app.goo.gl/trUu66cHaVjTi97r6 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 111 225 6829 | Link
194 | North Sinai (Gefgafa) | ABB | 2025-04-09 | MV SWGR 11KV for PS#12 | 1 | Rejected | Hyperlink |  | attached | 8700009007 | PO.308.68.1 | Ahmed Hammam | 0 10 06055246 | https://maps.app.goo.gl/trUu66cHaVjTi97r6 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
195 | Maghagha JV | SEGA.M | 2025-04-10 | Lighting Panels. Security Room (LEV.3)&DB-LAB (LEV.4)&DB-ADMIN (LEV.5)&DB- Store & Ware House (LEV.6)&DB- Air Blower Building (LEV.7)&DB-Sludge (LEV.8)&DB-Chlorination (LEV.9) | 7 | Approved with comments | Hyperlink |  | attached | 9600000792 | PO.218.59.2 | Hany Henry | 0 100 216 2226 | https://maps.app.goo.gl/6TwbXifJWZyDKM456 | N.A | N.A | N.A | Link
196 | Intake Mostakbal Misr | Giza Cables | 2025-04-13 | LV Cables 1*6 & 1*10 & 4*4 & 4*16 mm2 | As per attached | Approved | Hyperlink |  | attached | 8700009942 | PO.223.56.5 | Hassan Ali | 0 109 711 8883 | https://maps.app.goo.gl/YiRTzz6HfLJYb5vX6 | Hydro | Mohamed Samy | 0 100 782 8569 | Link
197 | Ain Sokhna | ABB | 2025-04-14 | MDB LV Panels (MDB-400V 02) | 1 | Approved with comments | Hyperlink |  | attached | 8700008407 | PO.344.59.1 | Marwa Magdy | 0 10 29046555 | https://maps.app.goo.gl/D7ZTAoMwkxga4dBZ6 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 11 12256829 | Link
198 | Ain Sokhna | Quassi | 2025-04-14 | Instrumentation | As per attached | Approved with comments | Hyperlink |  | attached | 8700009084 | PO.344.107.2 | Adnan Ghazy | 0 10 22623982 | https://maps.app.goo.gl/meJCLauWAdqN1RrJ8 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 11 12256829 | Link
199 | Assuit | UIC (El Sewedy Special Cables) | 2025-04-15 | Control Cables | As per attached | Approved | Hyperlink |  | attached | 8600100933 | 8600100933 | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | SEECO | N.A | N.A | Link
200 | Al Ayat Intake - Dahshoor Booster Pump | Stahl Crane | 2025-04-15 | Hoists 1 ton Jib Crane (Black Bear) | 2 | Rejected | Hyperlink | Email | attached | 8700010109 | PO.329.296.2 | Abd El Rahman | 0 120 464 4955 | https://maps.app.goo.gl/JCwBPGeqo22n5miX9 | Enviro | Ebraheem | 0 10 04615973 | Link
201 | Tahta treatment Plant | El sewedy EGYTECH (A3) | 2025-04-16 | MV & LV Cables | As per attached | Approved | Hyperlink |  | attached | 8700010452 | PO.192.56.3.sup.01 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/CNjYGqppnuLXbMhD9 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
202 | Tahta treatment Plant | Gilla | 2025-04-16 | Variable Speed Drive | 2 | Approved (TUV) | Hyperlink |  | attached | 8700009878 | PO.192.175.1 | Mahmoud Salem | 0 106 552 5118 | https://maps.app.goo.gl/5a5m6j33GPJ7LAFT8 | SABBOUR | Ahmed Ali | 0 10 62401340 | N.A
203 | Intake Mostakbal Misr | MTS Fire Fighting | 2025-04-17 | Fire Alarm System | As per attached | Approved | Hyperlink | Waiting final approval | attached | 8700009945 8700010115 | PO.223.160.8 PO.223.160.9.add.1 | Fady Saly | 0 127 459 1588 | https://maps.app.goo.gl/r6m6wKEjGDHJAYop7 | Hydro | Eslam Samir | 0 111 690 0592 | Link
204 | Al Ayat Intake - Dahshoor Booster Pump | Telecom Technology | 2025-04-19 | PABX System Panasonic | 1 | Approved | Hyperlink |  | attached | 8700010045 | PO.329.160.2 | Rabie Elkhodary | 0 120 770 2195 | https://maps.app.goo.gl/XX9ocBFtRvNAYcWv5 | Enviro | Fawzy Abd El Raouf | 0 122 788 6178 | Link
205 | Maghagha JV | MISR Crane for Engineering Work | 2025-04-20 | Cranes ( Monorail & JIB) for Maghagha JV Project | 10 | Approved | Hyperlink | Still Remaining El Sheikh Ziad -Sub | attached |  | PO.218.145.4 | Abd EL Rahman Mamdouh | 0 111 863 7357 | https://maps.app.goo.gl/7QTwvXMmNBXK1xDW8 | N.A | N.A | N.A | Link
206 | North Sinai (Gefgafa) | BICC | 2025-04-22 | LV Wires (3 & 4 & 6) mm2 | As per attached | Approved | Hyperlink |  | attached | 8700009707 | PO.308.56.1 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
207 | Zone.G | BICC | 2025-04-22 | LV Wires ( 3 & 4 & 6 ) mm2 | As per attached | Approved | Hyperlink |  | attached | 8700009480 | PO.339.56.2 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | HYDRO | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
208 | Maghagha JV | EMAS | 2025-04-23 | LV MDB | 5 | Approved with comments | Hyperlink |  | attached | 9600000749 | PO.218.59.5.SUP.01 | Mohamed Ali | 0 105 002 3103 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | N.A | N.A | N.A | Link
209 | Tahta treatment Plant | 2B (Hitachi/ABB) | 2025-04-27 | ABB Oil Transformers 1600 KVA 11/0.4 KV | 2 | Rejected | NO Report | Rejected to be not ready & FAT Done 20/05/2025 | attached | 8700009746 | PO.192.65.1 | Ahmed Fathy | 0 109 880 7718 | https://maps.app.goo.gl/VRe3T3wC7MWtNR848 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
210 | Tahta treatment Plant | Gilla / Schenider | 2025-04-27 | RMU ( 3 + 1 C.B) / 11 KV | 2 | Approved | Hyperlink |  | attached | 8700009879 | PO.192.68.1 | Mahmoud Salem | 0 106 552 5118 | https://maps.app.goo.gl/k8p94n7Ufjz5UyVp9 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
211 | Intake Mostakbal Misr | Giza Cables | 2025-04-28 | LV Cables Batch 02 | As per attached | Approved | Hyperlink |  | attached | 8700009942 | PO.223.56.5 | Hassan Ali | 0 109 711 8883 | https://maps.app.goo.gl/YiRTzz6HfLJYb5vX6 | Hydro | Mohamed Samy | 0 100 782 8569 | Link
212 | Port Said ( PS1 & PS2) | MK | 2025-04-29 | Fire Alarm system Simplex | As per attached | Approved | Hyperlink |  | attached | 8700008583 | PO.94.160.6 | Noura Rabea | 0 106 640 5858 | https://maps.app.goo.gl/t1CA5XLWyLBoTFzF7 | Dar El Hanadsa | N.A | N.A | Link
213 | Intake Mostakbal Misr | BICC | 2025-04-30 | LV Wires (3&4) mm2 | As per attached | Approved | Hyperlink |  | attached | 8700010295 | PO.223.56.6.Add.1 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | HYDRO | El Nagar | 0 10 98678092 | Link
214 | sanhour | EGYMAC | 2025-05-04 | Tranformers for Kiosks 150 & 200 & 500 KVA (Partial) | 6 | Approved | Hyperlink |  | attached | 8700008742 | PO.317.279.1 | Mohamed Samir | 0 10 09213617 | https://maps.app.goo.gl/6fmkWjQGsgzMGRwm8 | Stantic | Khaled Sayed | 0 11 43491374 | Link
215 | Zone.G | Schenider | 2025-05-04 | MV SWGR Item (1) | 1 | Approved with comments | Hyperlink |  | attached | 8700008696 | PO.339.68.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
216 | Ain Sokhna | HITEKNOFAL | 2025-05-05 | Fiber Optic Cables (HITEKNOFAL) | 3296 Meter | Approved | Hyperlink |  | attached | 8600109534 | 8600109534 | Mostafa Radwan | 0 101 060 0073 | https://maps.app.goo.gl/LY2F8n8LHScU59486 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 11 12256829 | Link
217 | North Sinai (Gefgafa) | Misr of Modern Crane | 2025-05-06 | Over Head Cranes ( Smart Steel) | 2 | Approved | Hyperlink |  | attached | 8700008873 | PO.308.145.2 | Mohamed Hussein | 0 100 852 0679 | https://maps.app.goo.gl/rPXX5VZTrfbHX1pb6 | Raouf Darwesh | N.A | N.A | Link
218 | Intake Mostakbal Misr | Giza Cables | 2025-05-07 | LV Cables Batch 03 | As per attached | Approved | Hyperlink |  | attached | 8700009942 | PO.223.56.5 | Hassan Ali | 0 109 711 8883 | https://maps.app.goo.gl/YiRTzz6HfLJYb5vX6 | Hydro | El Nagar | 0 10 98678092 | Link
219 | Zone.G | Schenider | 2025-05-08 | MV VFD Online at china 2200 KW 6.6 KV ATV6000C288A6666BA5 | 5 | Approved | Hyperlink |  | attached | 8700008695 | PO.339.175.1 | Ahmed Fawzy | 0 127 905 9616 | Online China | Hydro | Dr Badawy | 0 10 66866714 | N.A
220 | Tahta treatment Plant | El sewedy EGYTECH (A3) | 2025-05-11 | LV Cables (3*300 +150 mm2 &4*16 mm2) | As per attached | Approved | Hyperlink |  | attached | 8700010452 | PO.192.56.3.sup.01 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/CNjYGqppnuLXbMhD9 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
221 | Ain Sokhna | EL Hammam Fans | 2025-05-11 | Exhaust Fans | 23 | Approved | Hyperlink |  | attached | 8700009934 | PO.344.130.1 | Ahmed Eid | 0 128 516 3223 | https://maps.app.goo.gl/RAuAJc2BLsvtmnzs8 | ECR (Engineering Consultancy & Research) | Mohamed El Saied | 0 105 024 4472 | Link
222 | Sanhour | EGYMAC | 2025-05-12 | Kiosks 150 & 200 & 500 KVA | 6 | Approved | Hyperlink |  | attached | 8700008742 | PO.317.279.1 | Mohamed Samir | 0 10 09213617 | https://maps.app.goo.gl/6fmkWjQGsgzMGRwm8 | Stantic | Khaled Sayed | 0 11 43491374 | Link
223 | Port Said ( PS1 & PS2) | Orascom Trading | 2025-05-14 | Fire Pumps (Elec & Jockey & Diesel) AURORA | 3 |  | Hyperlink |  | attached | 8700010071 | PO.94.104.2 | Nesreen El Seufi | 0 112 777 6892 | https://maps.app.goo.gl/12MF1TU4QPjKtwv7A | Dar El Hanadsa | N.A | N.A | Link
224 | Zone.G | Schenider | 2025-05-15 | LV VFD Online at china | 53 | Approved | Hyperlink |  | attached | 8700008695 | PO.339.175.1 | Ahmed Fawzy | 0 127 905 9616 | Online China | Hydro | Dr Badawy | 0 10 66866714 | N.A
225 | Al Ayat Intake - Dahshoor Booster Pump | NEPTON | 2025-05-18 | Fire alram System | As per attached | Approved | Hyperlink |  | attached | 8700008250 | PO.342.104.1 | Hitham Mohamed | 0 109 992 7312 | https://maps.app.goo.gl/efTMqJnQ4vaiaaJB9 | Enviro | Fawzy Abd El Raouf | 0 122 788 6178 | Link
226 | El Hammam PS(1,2) | Schenider (Tricom) | 2025-05-19 | RTU for Pump Station (1&2) | 2 | Approved with comments | Hyperlink |  | attached | 8700005098 | PO.202.107.1 | Omar Assem | 0 127 898 6334 | https://maps.app.goo.gl/aHKospfVv7apcdWs8 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
227 | Tahta treatment Plant | Advance Water Treatment | 2025-05-19 | Chlorination & Alum. System | As per attached | Approved with comments | Hyperlink |  | attached | 8700009795 | Contract | Mosad El Sheikh | 0 109 872 9329 | https://maps.app.goo.gl/tuZQjH7vCQVwQrMh6 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
228 | Tahta treatment Plant | 2B (Hitachi/ABB) | 2025-05-20 | ABB Oil Transformers 1600 KVA 11/0.4 KV | 2 | Approved | Hyperlink |  | attached | 8700009746 | PO.192.65.1 | Ahmed Fathy | 0 109 880 7718 | https://maps.app.goo.gl/VRe3T3wC7MWtNR848 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
229 | Tahta treatment Plant | UIC (El Sewedy Special Cables) | 2025-05-20 | LV Wires (03 & 04 & 06) mm2 | As per attached | Approved | Hyperlink |  | attached | 8700010397 8700010237 | PO.192.56.4.sup.01 PO. 192.56.5 Add.01 | Moustafa Hassanien | 0 103 006 7130 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
230 | North Sinai (Gefgafa) | ABB | 2025-05-21 | Re-Inspection MV SWGR 11 KV for PS#12 & PS 13 | 1 | Approved with comments | Hyperlink |  | attached | 8700009007 | PO.308.68.1 | Ahmed Hammam | 0 10 06055246 | https://maps.app.goo.gl/trUu66cHaVjTi97r6 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
231 | NACWWTP | Remal | 2025-05-22 | Sound System | As per attached | Approved with comments | Hyperlink |  | attached | 8700009031 | PO.119.160.5 | Ibrahim Rizk | 0 11 55774747 | https://maps.app.goo.gl/9JbAaqbjR6rJ3NUU7 | AAW | Mamdouh Kamal | 0 111 821 5341 | Link
232 | Zone.G | Schenider (Tricom) | 2025-05-25 | PLC & RTU Automation System | As per attached | Approved | Hyperlink |  | attached | 8700008743 | PO.339.107.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/aHKospfVv7apcdWs8 | Hydro | Dr Badawy | 0 10 66866714 | Link
233 | Industrial Zone | Zaki El Sewedy | 2025-05-26 | Kiosk 50 KV 22/0.4 KV for Kiosk (Zaki Elsewedy ) | 8 | Rejected | NO Report |  | attached | 8700008773 | PO.342.279.1 | Walaa Mustafaa | 0 107 092 9657 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
234 | Lines October WTP | MECORR | 2025-05-26 | Cathodic Protection System | As per attached | Approved | Hyperlink |  | attached | 8700009486 |  | Mohamed Bian | 0 12 80380082 | https://maps.app.goo.gl/ZmfmWHEZS5j9hge2A | المركز القومي للبحوث | Mohamed Abd El Fatah | N.A | Link
235 | Tahta treatment Plant | KORRA ENERI | 2025-05-27 | Generators for Intake & Treatment Plant 800KVA | 1 | Approved | Hyperlink |  | attached | 8700010395 | PO.192.66.1 | Eslam Hamdy | 0 102 555 6067 | https://maps.app.goo.gl/TwWqJ7HhGVNksACs7 | SABBOUR | Khaled | 0 10 26087417 | Link
236 | Tahta treatment Plant | UPE | 2025-05-28 | Anti Water Hammer System | As per attached | Approved with comments | Hyperlink |  | atached | 8700009725 | Contract UPE | Mohamed Ghareb UPE | 0 11 24674000 | https://maps.app.goo.gl/RehdeD4HivkBXdNN6 | SABBOUR | Mohamed Kamal | 0 12 89632361 | Link
237 | Tahta treatment Plant | NOVA | 2025-05-29 | Penstocks (Remaining Actuators & Gearbox’s & spindles.) | 24 | Approved | Hyperlink |  | attached | 8700009789 | PO 192.296.1 PO 192.296.3 | Aref Helmy | 0 10 80053531 | https://maps.app.goo.gl/iZyEhsVtuZ5mfLkH8 | SABBOUR | Mohamed Kamal | 0 12 89632361 | Link
238 | Tahta treatment Plant | Helipower ( HPT) | 2025-06-01 | Priming System | As per attached | Approved with comments | Hyperlink |  | attached | 8700009859 | PO.192.314.1 | Ahmed El Sabakh | 0 10 98989919 | https://maps.app.goo.gl/ghxGf3aNrA7EKKTRA | SABBOUR | Mohamed Kamal | 0 12 89632361 | Link
239 | Industrial Zone | Zaki El Sewedy | 2025-06-02 | Kiosk 50 KV 22/0.4 KV for Kiosk (Zaki Elsewedy ) | 8 | Rejected | NO Report | Need approval for RTU to Control C.B`s | attached | 8700008773 | PO.342.279.1 | Walaa Mustafaa | 0 107 092 9657 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
240 | Sanhour | EMAS | 2025-06-03 | LV MDB & DB for Sanhour Project | As per attached | Approved | Hyperlink | Only for DB`s | attached | 8700009081 | PO. 317.59.1 PO. 317.59.2.adden.01 | Aya Yasser | 0 108 005 5285 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | Stantic | Khaled Sayed | 0 11 43491374 | Link
241 | Zone.G | El sewedy EGYTECH (A3) | 2025-06-15 | MV & LV Cables El Sewedy | As per attached | Approved | Hyperlink |  | attached | 8700010673 | PO.339.56.3 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/CNjYGqppnuLXbMhD9 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
242 | Sanhour | El sewedy EGYTECH (A1) | 2025-06-16 | (12-20 KV) MV Cables 3*300 mm2 AL/XLPE/STA/PVC (EGYTECH) | 3401 Meters | Approved | Hyperlink |  | attached | 8700010276 | PO.317.56.2 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/6iaeqPztf8uoVZmb7 | Stantic | Khaled Sayed | 0 11 43491374 | Link
243 | Industrial Zone | Watania (advanced Sys.) | 2025-06-17 | Fire Fighting Pumps (Jockey & Elec ) | As Per attached | Approved with comments | Hyperlink |  | attached | 8700008250 | PO.342.104.1 | Mohamed Gaber | 0 110 104 2683 | https://maps.app.goo.gl/JgEVKggLghgAWJNV8 | CEGMAN | Ahmed said | 0 106 704 7657 | Link
244 | Ain Sokhna | Energya | 2025-06-17 | Control Cables | As per attached | Approved | Hyperlink | Remaining 2*2*1.5 | attached | 8600105732 | 8600105732 | Karem | 0 10 03523466 | https://maps.app.goo.gl/q7Urdj2Bte6sywdL7 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 11 12256829 | Link
245 | Zone.G | UIC (El Sewedy Special Cables) | 2025-06-18 | LV Cables El Sewedy (Partial PO ) | As per attached | Approved | Hyperlink |  | attached | 8700010673 | PO.339.56.3 | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
N.A | Safaga | EL Hegaz company | 2025-06-18 | Spacers PVC (Duct Bank) | N/A |  | NO Report | Cancelled | attached | 8600114255 | PO 8600114255 | Ahmed Nagy | 0 109 002 3343 | https://maps.app.goo.gl/CwEtwRvB5PZfxyNQ6 | Hill International | Mohamed Mokhtar | 0 100 304 6759 | N.A
N.A | Safaga | GM | 2025-06-18 | PVC Pipes (Duct Bank) | N/A |  | NO Report | Cancelled | attached | 8600113244 | 8600113244 | Shokry Ahmed | 0 122 998 1743 | https://maps.app.goo.gl/z69dRCt2yWaiPxqp7 | Hill International | Mohamed Mokhtar | 0 100 304 6759 | N.A
246 | Zone.G | Schenider | 2025-06-22 | LV Panels DB-PUMP PS 21 & 23 & 24 & 25 | 4 | Rejected | NO Report |  | attached | 8700008694 | PO.339.59.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/5mV4RwzdBGZoqSbi8 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
247 | Abou Oweikal | Elsewedy Steel | 2025-06-23 | Lighting Pole 2.5 Meter | As per attached | Approved | Hyperlink |  | attached | 8700004709 | PO.84.77.1 | Ayman El Sewedy | 0 114 282 1320 | https://maps.app.goo.gl/yMyNtTd8iMK14MLi8 | Misr Consultant | Kenawy Shaban | 0 11 51988877 | Link
248 | Zone.G | Taqnor | 2025-06-24 | Lighting Fixtures | As per attached | Approved with comments | Hyperlink | Waiting approval Material List | attached |  | PO.339.76.1 | Waleed Nassem | 0 10 99410899 | https://maps.app.goo.gl/xXGkKocattxr2tZh9 | Hydro | Mohamed Abd El Mohaimn | 0 111 323 3463 | Link
249 | Ain Sokhna | El sewedy EGYTECH (A3) | 2025-06-29 | LV Cable 3*150+70 mm2 CU/XLPE/CT/PVC | 519 | Approved | Hyperlink |  | attached | 8700010771 | PO.344.56.3 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/hGMWPmELQdT6H6GE7 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 11 12256829 | Link
250 | Al Ayat Intake - Dahshoor Booster Pump | FMTU ( Force MTU Power Sys.) | 2025-06-29 | Fuel Tanks for Diesel Generator ( Weekly 40000 & Daily 4500 m3) | 8 | Approved | Hyperlink |  | attached | 8700009325 | PO.329.66.1 | Riham Raafat | 0 106 157 7557 | https://maps.app.goo.gl/ZQbfgeM3JH9CWbjW8 | Enviro | Ebraheem | 0 100 461 5973 | Link
251 | Toshka Zone.S | SPEC | 2025-07-02 | Remaining Data Switches | As per attached | Approved | Hyperlink |  | attached | 8700009955 | PO.307.160.2 | Karim Safwat | 0 101 181 9701 | https://maps.app.goo.gl/S6pKZXFUvo4VUzZi6 | Cairo University | Abeer | 0 122 770 9514 | Link
252 | Tahta treatment Plant | AtlasCopco | 2025-07-06 | Air compressor with accssories & Vessel | 2 | Approved with comments | Hyperlink |  | attached | 8700010605 | PO.192.88.2 | Mohamed Samy | 0 12 88583293 | https://maps.app.goo.gl/ZJMfBF9gY2Np2nLD9 | SABBOUR | Mohamed Kamal | 0 12 89632361 | Link
253 | Al Ayat Intake - Dahshoor Booster Pump | Stahl Crane | 2025-07-08 | Hoists 1 ton Jib Crane (Winchy) | 2 | Approved | Hyperlink |  | attached | 8700010109 | PO.329.296.2 | Abd El Rahman | 0 120 464 4955 | https://maps.app.goo.gl/JCwBPGeqo22n5miX9 | Enviro | Ebraheem | 0 10 04615973 | Link
254 | Sanhour | RMG | 2025-07-09 | Control Panels for MDB for EMAS & Instrumentations | 3 | Rejected | NO Report | Panels not Ready | attached | 8700011238 | PO.317.107.1 | Esam | 0 11 115 65554 | https://maps.app.goo.gl/EWFzHoavYSAstZxQ9 | Stantic | Khaled Sayed | 0 11 43491374 | Link
255 | North Sinai (Gefgafa) | El sewedy EGYTECH (A1) | 2025-07-10 | MV Cable 3*240 mm2 CU/XLPE/PVC (12-20KV) | 797 Meters | Approved | Hyperlink |  | attached |  | PO.308.56.4 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/6iaeqPztf8uoVZmb7 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
256 | Zone.G | Total Power | 2025-07-14 | LV Panel Farmer | 30 | Approved | Hyperlink |  | attached | 8700010190 | PO.339.59.2 | Mohamed Alaa | 0 11 46885965 | https://maps.app.goo.gl/tPXETrhpUWMrqJgP7 | Hydro | Hassan Saber | 0 103 302 4669 | Link
257 | Abou Oweikal | TIBA | 2025-07-15 | AHU ( Centeral Air Condition Sys.) Manzalawi Group | 4 | Approved | Hyperlink |  | attached | 8700009948 | PO.84.131.1 | Mohamed Bebars | 0 12 00287335 | https://maps.app.goo.gl/YZ3yMxGHVZSAX6ar7 | Misr Consultant | Kenawy Shaban | 0 11 51988877 | Link
258 | Al Ayat Intake - Dahshoor Booster Pump | GEMKA | 2025-07-16 | Coarse Screen | 2 | Approved | Hyper Link | GearBox & Motor not approved | attached | 8700009055 | PO.329.296.1 | ahmed Soultan | 0 11 52289212 | https://maps.app.goo.gl/7VDKweb4FsGeQeim6 | Enviro | Ebraheem | 0 10 04615973 | Link
259 | El Borsa | Energya | 2025-07-20 | LV Cables 3*3 CU / PVC / PVC | 1295 | Approved | HyperLink |  | attached | 8700010801 | PO.189.56.3 | Karem | 0 10 03523466 | https://maps.app.goo.gl/q7Urdj2Bte6sywdL7 | Hydro | Mahmoud Roushdy | 0 10 06578257 | Link
260 | El Borsa | El sewedy EGYTECH (A1) | 2025-07-20 | LV Cable 4*25 mm2 AL/XLPE/STA/PVC | 2975 | Approved | HyperLink |  | attached | 8700010515 | PO.189.56.2 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/6iaeqPztf8uoVZmb7 | Hydro | Mahmoud Roushdy | 0 10 06578257 | Link
261 | New Delta 2 | Systech (Total Power) | 2025-07-21 | PLC & Marshalling Control Panel (Total Power) | 1 | Approved with comments | HyperLink |  | attached | 8700006960 | PO.259.107.1 | Ahmed Alaa | 0 114 688 5965 | https://maps.app.goo.gl/tPXETrhpUWMrqJgP7 | Raouf Darwesh | Ahmed El Ethnawy | 0 100 853 1149 | Link
262 | Tahta treatment Plant | Gilla | 2025-07-22 | LV Panels (MDB & DB) | As per attached | Approved with comments | Hyperlink |  | attached | 8700009880 8700010208 | PO. 192.59.1 PO. 192.59.2.adden.1 | Mahmoud Salem | 0 106 552 5118 | https://maps.app.goo.gl/k8p94n7Ufjz5UyVp9 | SABBOUR | Mahmoud Madbouly | 0 10 08452679 | Link
263 | Ain Sokhna | Advanced WareHouse | 2025-07-23 | Aerosol System | As per attached | Approved | Hyperlink |  | attached | 8700010732 | PO.344.116.2 | Hamdy Zidan Watania | 0 11 54888774 | https://maps.app.goo.gl/3S5YvqrwkY8KV1Xo6 | ECR (Engineering Consultancy & Research) | Mohamed El Halwany | 0 10 29660484 | Link
264 | Ain Sokhna | EL-Amana | 2025-07-23 | Cholirination Dosing system | As per attached | Approved | Hyperlink |  | attached | 8700009852 | Contract | Marwa | 0 10 11231174 | https://maps.app.goo.gl/y6aSkaTEnR93hYZG9 | ECR (Engineering Consultancy & Research) | Mohamed El Halwany | 0 10 29660484 | Link
265 | Tahta treatment Plant | Advance Water Treatment | 2025-07-27 | Chlorination Containers | 8 | Approved | Hyperlink |  | attached | 8700009795 | Contract | Mosad El Sheikh | 0 109 872 9329 | https://maps.app.goo.gl/tuZQjH7vCQVwQrMh6 | SABBOUR | N.A | N.A | Link
266 | Tahta treatment Plant | UIC (El Sewedy Special Cables) | 2025-07-27 | Control Cables | As per attached | Approved | Hyperlink |  | attached | 8700010397 8700010237 | PO. 192.56.4.sup.01 PO. 192.56.5.adden.01 | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | SABBOUR | N.A | N.A | Link
267 | North Sinai (Gefgafa) | UIC (El Sewedy Special Cables) | 2025-07-28 | LV Cables (Batch 01) | As per attached | Approved | Hyperlink |  | attached |  | PO.308.56.3 | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
268 | Tahta treatment Plant | EL Babtain | 2025-07-27 | Lighting Poles EL Babtain Lenghth 10 Meter | As per attached | Approved | Hyperlink | Galvanized Certificate | attached | 8600112455 | 8600112455 | Ahmed Abou Zaied | 0 102 237 3707 | https://maps.app.goo.gl/StYiQ9gKPcdJXjw2A | SABBOUR | N.A | N.A | Link
269 | Tahta treatment Plant | EL Hammam Fans | 2025-07-27 | Exhaust Fans | As per attached | Approved | Hyperlink |  | attached | 8700010546 | PO.192.130.1 | Kamel Hegazy | 0 12 73341666 | https://maps.app.goo.gl/RAuAJc2BLsvtmnzs8 | SABBOUR | N.A | N.A | Link
270 | U-Section | Energya | 2025-07-30 | LV Wires 03 & 04 & 06 mm2 | As per attached | Approved | Hyperlink |  | attached | 8700010093 | PO.356.56.1 | Karem | 0 10 03523466 | https://maps.app.goo.gl/q7Urdj2Bte6sywdL7 | Hydro | N.A | N.A | Link
271 | Tahta treatment Plant | COMET | 2025-07-31 | Main Motors WEG | As per attached | Approved | Hyperlink |  | attached | 8700009790 | PO.192.151.2 | Sherif Moustafa | 0 100 918 1824 | https://maps.app.goo.gl/PbzNaQ5Kzec14kZ88 | SABBOUR | N.A | N.A | Link
272 | Tahta treatment Plant | BICC | 2025-07-31 | Wires & LV Cables | As per attached | Approved | Hyperlink |  | attached | 8700010425 | PO.192.56.6 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | SABBOUR | N.A | N.A | Link
273 | Tahta treatment Plant | SynchroMisr | 2025-08-03 | Street Lighting Panels | 4 | Approved | Hyperlink |  | attached | 8700010587 | PO.192.59.3 | Alaa Khaled Hassan | 0 10 96569167 | https://maps.app.goo.gl/EaFdRx7bT18hRwav5 | SABBOUR | N.A | N.A | Link
274 | Tahta treatment Plant | Capital Guard | 2025-08-03 | CO2 / FM 200 System Fire Fighting | As per attached | Approved | Hyperlink |  | attached | 8700011226 | PO.192.116.1 | Ahmed Mohsen | 0 11 12289372 | https://maps.app.goo.gl/2aJf5Pmbahgzvn1k6 | SABBOUR | N.A | N.A | Link
275 | Sanhour | RMG | 2025-08-04 | Control Panels for MDB for EMAS & Instrumentations | 3 | Approved | Hyperlink |  | attached | 8700011238 | PO.317.107.1 | Esam | 0 11 115 65554 | https://maps.app.goo.gl/EWFzHoavYSAstZxQ9 | Stantic | Galal Stantic | 0 11 46257030 | Link
276 | Tahta treatment Plant | Taqnor | 2025-08-05 | Lighting Fixtures | As per attached | Approved | Hyperlink |  | attached | 8700010586 | PO.192.76.1 | Waleed Nassem | 0 10 99410899 | https://maps.app.goo.gl/xXGkKocattxr2tZh9 | SABBOUR | N.A | N.A | Link
277 | Sanhour | Alfa Lighting Fixture | 2025-08-10 | Lighting fixtures ALFA | As per attached | Approved | NO Report | Inspection at Site | attached | 8600091103 | 8600091103 | Ali Gebriel | 0 10 25171772 | https://maps.app.goo.gl/5k8sy5PYT24FuTmt8 | Stantic | N.A | N.A | Link
278 | Zone.G | El sewedy EGYTECH (A1) | 2025-08-12 | LV Cables | As per attached | Approved | Hyperlink |  | attached | 8700010673 | PO.339.56.3 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/GAbPw8cJjuRzeKbr6 | Hydro | Alaa Masood | 0 12 02004447 | Link
279 | Al Ayat Intake - Dahshoor Booster Pump | Egytrafo | 2025-08-13 | Oil Impressed Transformers 11/0.4 KV | 4 | Rejected | No Report | Rated Voltage must be 10.5 KV & Buchlouz Relay | attached | 8700008052 | PO.329.65.1 | Mahmoud Bakry | 0 10 70567908 | https://maps.app.goo.gl/8qAyhwCsJor1Z7ec6 | Enviro | Fawzy Abd El Raouf | 0 122 788 6178 | Link
280 | Maghagha JV | CPT Cusomized Power Technology | 2025-08-14 | Generators 110 KVA (Manshat Lamloum & Bani Khalf) | 2 | Approved | Hyperlink | Wiring Diagram & Batteries & Battery Charger & Control Panel & Fuel Pump | attached | 9600001065 | PO.218.66.2 | Ahmed Abdel Salam | 0 11 02558700 | https://maps.app.goo.gl/WH9s5Wk1LktYJeWF7 | N.A | N.A | N.A | Link
281 | RORO | SIGMA | 2025-08-17 | UPS 40K ABB (New Replacement) | 1 | Approved | Hyperlink |  | attached | 8700007286 | N.A | Sameh Saad | 0 10 13308831 | https://maps.app.goo.gl/ZeistnrMTQDc7qoNA | Shaker Consultant | Ehab Zaki | 0 100 661 9889 | Link
282 | Industrial Zone Waste water Plant | Egytrafo | 2025-08-18 | Dry Transformer Service 1000 KVA / Waste Water Plant | 2 | Approved | Hyperlink |  | attached | 8700010312 | PO.342.65.4.Sup.1 | Mahmoud Bakry | 0 10 70567908 | https://maps.app.goo.gl/8qAyhwCsJor1Z7ec6 | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
283 | Tahta treatment Plant | COMET | 2025-08-19 | Main Pumps KSB | As per attached | Approved | Hyperlink |  | attached | 8700009790 | PO.192.151.2 | Sherif Moustafa | 0 100 918 1824 | https://maps.app.goo.gl/jEzUzjS6ev24rtsw5 | SABBOUR | N.A | N.A | Link
284 | Tahta treatment Plant | NOVA | 2025-08-19 | Actuators for Penstocks | 12 | Approved | Hyperlink |  | attached | 8700009789 | PO.192.296.3 | Aref Helmy | 0 10 80053531 | https://maps.app.goo.gl/iZyEhsVtuZ5mfLkH8 | SABBOUR | N.A | N.A | Link
285 | Zone.G | UIC (El Sewedy Special Cables) | 2025-08-19 | LV Cables | As per attached | Approved | Hyperlink |  | attached | 8700010673 | PO.339.56.3 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/NkHLwCBhN37DgVWC7 | Hydro | Alaa Masood | 0 12 02004447 | Link
286 | Toshka Zone.S | MISR Crane for Engineering Work | 2025-08-20 | OverHead Crane 20 & 16 Tons | 2 | Approved | Hyperlink |  | attached |  | PO 307.145.3 | Abd EL Rahman Mamdouh | 0 111 863 7357 | https://maps.app.goo.gl/7QTwvXMmNBXK1xDW8 | Cairo University | Mohamed Sofar | 0 11 45117582 | Link
287 | 6 October tretment Plant | RO-TECH | 2025-08-23 | Fire Alarm system Simplex | As per attached | Approved | Hyperlink |  | attached | 8700011061 | PO.159.160.6 | Hamza Mahmoud | 0 10 96561201 | N.A | Enviro | N.A | N.A | Link
288 | Zone.G | Schenider | 2025-08-24 | LV DB-Panels ADMIN & PS 11 &(18,19,26,27,61,64)&(24&25)(20,63)&(21,23) | As per attached | Approved with comments | Hyperlink | attached Report | attached | 8700008694 | PO.339.59.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/k6MPEXBdco6r31nPA | Hydro | Alaa Masood | 0 12 02004447 | Link
289 | Assuit | Engineering for ElectroMechanical equipment(Sakrgugaw) | 2025-08-25 | Dewatering Pumps | 2 | Approved | Hyperlink |  | attached | 8700010880 | PO.101.151.8 | Mohamed Mahdy | 0 122 650 0536 | https://maps.app.goo.gl/jeJScTEbksz2Purx7 | SEECO | N.A | N.A | Link
290 | Intake Mostakbal Misr | UIC (El Sewedy Special Cables) | 2025-08-26 | Samples Control Cables | As per attached | Approved | Hyperlink |  | attached | 8600112672 8600113080 | 8600112672 & 8600113080 | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Hydro | Mohamed Samy | 0 10 07828569 | Link
291 | Abou Oweikal | UIC (El Sewedy Special Cables) | 2025-08-26 | LV Cables 4*16 & 16 mm2 | 1300 | Approved | Hyperlink |  | attached | 8700010796 | PO.84.56.13 | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Misr Consultant | Kenawy Shaban | 0 11 51988877 | Link
292 | New Delta 2 | Schenider | 2025-08-27 | MVSWGR 22 KV | 1 | Approved with comments | Hyperlink | attached Report | attached | 8700009326 | PO.259.68.1 | Farida Helaly | 0 12 88283333 | https://maps.app.goo.gl/k6MPEXBdco6r31nPA | Raouf Darwesh | Ahmed El Ethnawy | 0 100 853 1149 | Link
293 | Al Ayat Intake - Dahshoor Booster Pump | Egytrafo | 2025-08-31 | Oil Transformers 11 / 0.4 KV | 4 | Approved | report |  | attached | 8700008052 | PO.329.65.1 | Mahmoud Bakry | 0 10 70567908 | https://maps.app.goo.gl/8qAyhwCsJor1Z7ec6 | Enviro | Fawzy Abd El Raouf | 0 122 788 6178 | Link
294 | New Delta 2 | Schenider | 2025-09-01 | MVSWGR 11 KV | 1 |  | Hyperlink |  | attached | 8700009326 | PO.259.68.1 | Farida Helaly | 0 12 88283333 | https://maps.app.goo.gl/k6MPEXBdco6r31nPA | Raouf Darwesh | Ahmed El Ethnawy | 0 100 853 1149 | Link
295 | Maghagha JV | Esc | 2025-09-01 | Maghagha Submersible Sewage Pumps (Abbasia West) | 4 | Approved | Hyperlink |  | attached | 9600000848 | PO.218.151.4 PO.218.151.5 | Mohamed abd Elnasser | 0 128 781 6955 | https://maps.app.goo.gl/zYcskUYYtLZmpTME6 | N.A | N.A | N.A | Link
296 | Tahta treatment Plant | lectro Power - El Habashy | 2025-09-02 | BusWay 3200 A WWTP for Treatment Plant | As per attached | Approved | Hyperlink |  | attached | 8700009815 | Contract 192-58-01 | Fares Khaled | 0 110 160 0909 | https://maps.app.goo.gl/i7gCszWecJs1Cn6bA | SABBOUR | N.A | N.A | Link
297 | North Sinai (Gefgafa) | El sewedy EGYTECH (A3) | 2025-09-03 | LV Cables (Batch 02) | As per attached | Approved | Hyperlink |  | attached |  | PO.308.56.2 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/hGMWPmELQdT6H6GE7 | Raouf Darwesh | Saied negm | 0 101 187 2255 | Link
298 | Abou Oweikal | TIBA | 2025-09-03 | CU Units TSCU-100 | 4 | Approved | Hyperlink |  | attached | 8700006030 | PO.84.103.1 | Mohamed Bebars | 0 12 00287335 | https://maps.app.goo.gl/YZ3yMxGHVZSAX6ar7 | Misr Consultant | Mohamed Abbas | 0 11 50575814 | Link
299 | Industrial Zone | ESC (FGECO) | 2025-09-08 | Re- Inspection after Damage Local Control Panel for Booster & Circulation Pumps | 2 | Approved | Hyperlink | Change Damage | attached | 8700008249 | PO.342.151.1 | Mohamed abd Elnasser | 0 128 781 6955 | https://maps.app.goo.gl/QNZDGUdfhJ2JYbwq8 | CEGMAN | N.A | N.A | Link
300 | Maghagha JV | BICC | 2025-09-11 | LV Cables From BICC for Treatment Plant | As per attached | Approved | Hyperlink |  | attached | 9600000800 | PO.218.56.3 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | N.A | N.A | N.A | Link
301 | Tahta treatment Plant | Advance Water Treatment | 2025-09-15 | Air Blowers for Chlorination System | 2 | Approved | Hyperlink | NOPWASD | attached | 8700009795 | Contract | Mosad El Sheikh | 0 109 872 9329 | https://maps.app.goo.gl/tuZQjH7vCQVwQrMh6 | SABBOUR | N.A | N.A | Link
302 | Tahta treatment Plant | TCC | 2025-09-15 | Fire alarm system Model ETON | As per attached | Approved | Hyperlink | Remaining Beam &Sirens | attached | 8700011195 | PO.192.160.1 | Milad Gayed | 0 12 24652118 | https://maps.app.goo.gl/CYNJHjPPPdjMLxm87 | SABBOUR | N.A | N.A | Link
303 | Tahta treatment Plant | SPEC | 2025-09-15 | Telephone System (SPEC) | As per attached | Approved | Hyperlink | Remaining switches & servers | attached | 8700011067 | PO.192.160.2 | Karim Safwat | 0 101 181 9701 | https://maps.app.goo.gl/S6pKZXFUvo4VUzZi6 | SABBOUR | N.A | N.A | Link
304 | Zone.G | El sewedy EGYTECH (A3) | 2025-09-16 | LV MICA Cable 3X150+70 mm2 - [Cu/MICA/XLPE/SWA/PVC]. | 373 | Approved | Hyperlink |  | attached | 8700010673 | PO.339.56.3 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/CNjYGqppnuLXbMhD9 | Hydro | Mohamed abd El Mohaymen | 0 11 13233463 | Link
305 | El Hammam PS(1,2) | UIC (El Sewedy Special Cables) | 2025-09-17 | Control Cables | As per attached | Approved | Hyperlink |  | attached | 8600114148 | attached | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Hydro | Fathy El Esawy | 0 10 08331443 | Link
306 | Zone.G | UIC (El Sewedy Special Cables) | 2025-09-23 | Control & Fire Alarm Cables | As per attached | Approved | Hyperlink |  | attached | 8600115042 8600109937 | attached | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Hydro | Mohamed abd El Mohaymen | 0 11 13233463 | Link
307 | Sanhour | EL Babtain | 2025-09-24 | Street Lighting Poles with Solar Cell & Fixtures | 6 | Approved | Hyperlink |  | attached | 8600091103 | 8600091103 | Ahmed Abou Zaied | 0 102 237 3707 | https://maps.app.goo.gl/StYiQ9gKPcdJXjw2A | Stantic | Khaled Sayed | 0 11 43491374 | Link
308 | NACWWTP | BICC | 2025-09-28 | LV Cables 4*16 mm2 (AL) & 1*16 mm2 (CU) | As per attached | Approved | Hyperlink |  | attached | 8700010581 | PO.119.56.4.Adden.02 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | AAW | Fathy Mohamed | 0 12 73175249 | Link
309 | Maghagha JV | EL Hammam Fans | 2025-10-01 | Exhaust Fans | 16 | Approved | Hyperlink |  | attached | 9600000740 | PO 218.130.1 PO 218.130.3 | Ahmed Eid | 0 128 516 3223 | https://maps.app.goo.gl/RAuAJc2BLsvtmnzs8 | N.A | N.A | N.A | Link
310 | Tahta treatment Plant | Misr of Modern Crane | 2025-10-04 | Steel Work for Monorails Cranes | 9 | Approved | Hyperlink |  | attached | 8700009782 | PO.192.145.1 | Mohamed Hussein | 0 100 852 0679 | https://maps.app.goo.gl/rPXX5VZTrfbHX1pb6 | SABBOUR | N.A | N.A | Link
311 | Zone.G | Sakr | 2025-10-05 | Trash Cleaning Machine | 1 | Approved | Hyperlink |  | attached | 8700008413 | PO.339.296.3 | Hesham | 0 10 08886559 | https://maps.app.goo.gl/LxfzLWUsKXrJZuTY6 | Hydro | Abd Allah El Dehiny | 0 11 10068758 / 01024666664 | Link
312 | Industrial Zone | Zaki El Sewedy | 2025-10-06 | Kiosk 50 KV 22/0.4 KV for Kiosk (Zaki Elsewedy ) | 4 | Approved | Hyperlink |  | attached | 8700008773 | PO.342.279.1 | Walaa Mustafaa | 0 107 092 9657 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
313 | Tahta treatment Plant | ROSENBERG | 2025-10-07 | (Supply & Exhaust) Fans | 14 | Approved | Hyperlink |  | attached | 8700011216 | PO.192.130.3 | Marco Kamal | 0 103 083 9722 | https://maps.app.goo.gl/6rUF5xwtWX5vkvhF9 | Sabbour | N.A | N.A | Link
314 | Tahta treatment Plant | Advance Water Treatment (Electric Technology) | 2025-10-07 | Control Panels for Chlorine & chemical system(WTP) | 3 | Approved | Hyperlink |  | attached | 8700009795 | Contract | Ahmed Hany | 0 10 05104803 | https://maps.app.goo.gl/JYDALgGbmV9beAPz5 | Sabbour | Ahmed Ali | 0 10 62401340 | Link
315 | Toshka Zone.S | ICE | 2025-10-08 | Cathodic Protection ICE | As per attached | Rejected | No Report | New Request from MED | attached | 8700009195 | Contract | Ehab Ayman | 0 100 709 0897 | https://maps.app.goo.gl/WvHTgdAD37p2zqo17 | Cairo University | Fahmy Yasser | 0 12 79380575 | Link
316 | Zone.G | Schenider | 2025-10-12 | LV DB-Panels (Lighting & Power) | As per attached | Approved | Hyperlink |  | attached | 8700009326 | PO.259.68.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/k6MPEXBdco6r31nPA | Hydro | Alaa Masood | 0 12 02004447 | Link
317 | Tahta treatment Plant | NOVA | 2025-10-20 | Weir for Calrifier Tanks | As per attached | Approved | Hyperlink |  | attached | 8700011211 | PO.192.296.5 | Aref Helmy | 0 10 80053531 | https://maps.app.goo.gl/iZyEhsVtuZ5mfLkH8 | SABBOUR | N.A | N.A | Link
318 | Ain Sokhna | Taqnor | 2025-10-20 | Lighting Fixtures | 33 | Approved | Hyperlink |  | attached | 8700010906 | PO.344.76.1 | Waleed Nassem | 0 10 99410899 | https://maps.app.goo.gl/xXGkKocattxr2tZh9 | ECR (Engineering Consultancy & Research) | Ahmed Esam | 0 111 225 6829 | N.A
319 | Industrial Zone Waste water Plant | Novovent Fans | 2025-10-20 | Exhaust Fans for Waste Water plant | 2 | Approved | Hyperlink |  | attached | 8700010969 | PO.342.130.3 | Ahmed Salah | 0 122 299 8517 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | CEGMAN | N.A | N.A | N.A
320 | Tahta treatment Plant | Engineering Group | 2025-10-27 | Telescopic valves | 2 | Approved | Hyperlink |  | attached | 8600121897 | 8600121897 | Tamer | 0 10 06614646 | https://maps.app.goo.gl/CeKXPAmbMAx8RyRn8 | SABBOUR | N.A | N.A | Link
321 | Toshka Zone.S | MISR Crane for Engineering Work | 2025-10-27 | Metal works for Crane 16 tons | As per attached | Approved | Hyperlink |  | attached |  | PO 307.145.3 | Abd EL Rahman Mamdouh | 0 111 863 7357 | https://maps.app.goo.gl/7QTwvXMmNBXK1xDW8 | Cairo University | Mohamed Sofar | 0 11 45117582 | Link
322 | Tahta treatment Plant | Gilla | 2025-10-28 | Remaining LV Panels ( Auxiliary Panel , MDB – WTP , MDB – Fire Tank,LVP , LCP – Intake × 5 , LCP – PWTP × 4) | As per attached | approved with comments | Hyperlink |  | attached |  | PO. 192.59.1 PO. 192.59.2.adden.1 | Mahmoud Salem | 0 106 552 5118 | https://maps.app.goo.gl/k8p94n7Ufjz5UyVp9 | SABBOUR | Ahmed Ali | 0 10 62401340 | Link
323 | Zone.G | PETRA | 2025-10-29 | Air Handling Units | 2 | Approved | Hyperlink |  | attached | 8700008738 | PO 339.131.1 | Ahmed Youssef | 0 11 16977710 | https://maps.app.goo.gl/C5cwST5SS7be5bHcA | Hydro | Mohamed El Shafeey | 0 10 33379444 | Link
324 | 6 October tretment Plant | NAFFCO Fire Search | 2025-10-29 | Fire Search NAFFCO | As per attached | Approved | Hyperlink |  | attached | 8600120145 | 8600120145 | Ahmed Abd El Nasser | 0 12 79242003 | https://maps.app.goo.gl/jR6bR7soBvyDFaKE9 | Enviro | Gamal Badeir | 0 11 17397557 | Link
325 | Al Ayat Intake - Dahshoor Booster Pump | Stahl Crane (warehouse) | 2025-11-11 | Hoists Over Head 12.5 & 10 Tons | 4 | Approved | Hyperlink |  | attached |  | PO 329.145.1 | Abd El Rahman | 0 120 464 4955 | https://maps.app.goo.gl/8EnkyG3jaxMZhLhy8 | Enviro | Ebraheem | 0 10 04615973 | Link
326 | Maghagha JV | CPT Cusomized Power Technology | 2025-11-13 | Generators 110 KVA (Abassia West) | 1 | Approved | Hyperlink |  | attached | 9600001065 | PO.218.66.2 | Beshoy | 0 11 26499223 | https://maps.app.goo.gl/WH9s5Wk1LktYJeWF7 | N.A | N.A | N.A | Link
327 | Sanhour | EMAS | 2025-11-17 | MDB & PLC (RMG) | 3 | Approved | Hyperlink |  | attached | 8700009081 | PO. 317.59.2.adden.01 & PO.317.107.1 | Omar Fouad | 0 10 66050093 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | EGAC | DR Nader | 0 12 23817600 | Link
328 | Maghagha JV | ESC | 2025-11-20 | Maghagha Submersible Sewage Pumps (Abbasia East) | 4 | Approved | Hyperlink |  | attached |  | PO. 218.151.5 | Mohamed abd Elnasser | 0 128 781 6955 | https://maps.app.goo.gl/zYcskUYYtLZmpTME6 | N.A | N.A | N.A | Link
329 | Safaga | MPS Ware House (Schenider - UPS) | 2025-11-20 | UPS Schenider (Batteries Later) | As per attached | approved with comments | Hyperlink |  | attached |  | PO. 375.64.1 | Sara Esmail | 0 10 11379952 | https://maps.app.goo.gl/V3PieHHuuYXU4EFW7 | Hill International | Ahmed Salem | 0 12 77753326 | N.A
330 | Assuit | Egytrafo | 2025-11-30 | Oil Transformer 2.5 MVA 11/3.3 KV | 1 | Approved | Hyperlink |  | attached |  | PO. 101.65.5 | Haidy Nageeb | 0 112 228 9462 | https://maps.app.goo.gl/8qAyhwCsJor1Z7ec6 | SEECO | Fares | 0 100 158 6256 | Link
331 | Zone.G | Schenider | 2025-12-01 | LV Panels (HVAC DP -Vent) | 2 | approved with comments | Hyperlink |  | attached | 8700009326 | PO.259.68.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/k6MPEXBdco6r31nPA | Hydro | Alaa Masood | 0 12 02004447 | Link
332 | El Borsa | EMAS | 2025-12-03 | Kiosks 630 KVA | 1 | approved with comments | Hyperlink | Still Waiting FAT Transformer | attached |  | PO.189.68.2 | Nahed Ahmed | 0 10 29974497 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | Hydro | Mahmoud Roushdy | 0 10 06578257 | Link
333 | Sanhour | Mantrac | 2025-12-09 | Emergency Diesel Generator (80&135&350)KVA & Fuel System | 3 | Approved | Hyperlink | Except Tanks | attached | 8700009655 | PO. 317.66.1 | Shady Khaled | 0 12 25250120 | https://maps.app.goo.gl/sMnsWiEdPoKHbPgV6 | Stantic | Rabee | 0 10 05851398 | Link
334 | sanhour | UIC (El Sewedy Special Cables) | 2025-12-15 | Control Cables at El Sewedy (UIC) | As per attached | Approved | Hyperlink |  | attached |  | 8600119878 | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | Stantic | Rabee | 0 10 05851398 | Link
335 | T.Lines (New Administration Capital) | UIC (El Sewedy Special Cables) | 2025-12-16 | Control Cables at El Sewedy (UIC) | As per attached | Approved | Hyperlink |  | attached | 8600119504 | 8600119504 | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | ECG | Kareem | 0 10 00828100 | Link
336 | Abou Oweikal | El sewedy EGYTECH (A3 ) | 2025-12-17 | LV Cables Earth 1*120 & 1*150 mm2 | As per attached | Approved | Hyperlink |  | attached |  | PO. 84.56.14 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/CNjYGqppnuLXbMhD9 | Misr Consultant | Kenawy Shaban | 0 11 51988877 | Link
337 | El Borsa | El Sewedy (Transformers) | 2025-12-17 | Dry Transformers 630 KVA 22/0.4 KV for Kiosk 630KVA | 1 | Approved with Comments | Hyperlink | Surrge arrestor | attached |  | PO.189.68.2 | Nahed Ahmed | 0 10 29974497 | https://maps.app.goo.gl/ewefwJ1nYefmTEau6 | Hydro | Mahmoud Roushdy | 0 10 06578257 | Link
338 | Port Said ( PS1 & PS2) | lectro Power - El Habashy | 2025-12-21 | Busway Port Said ( PS1 & PS2) | 1 | Approved with Comments | Hyperlink | Cooper Bar Dimenstion | attached |  | Contract HAC-02-HCI-94-58-01 | Mustafa Bahnasi | 0 110 160 0909 | https://maps.app.goo.gl/i7gCszWecJs1Cn6bA | Dar El Hanadsa | Mohamed Yehia | 0 10 08661411 | Link
339 | Tahta treatment Plant | Total Power | 2025-12-23 | DB LV Service Panels | As per attached | Approved | Hyperlink |  | attached |  | PO.192.59.5 | Moustafa El Attar | 0 109 955 8389 | https://maps.app.goo.gl/tPXETrhpUWMrqJgP7 | SABBOUR | N.A | N.A | Link
340 | 1500 Lines | Ateb | 2025-12-24 | Actuators for Valves | 20 | Approved | Hyperlink |  | attached |  |  | Yara Wageh | 0 127 665 5505 | https://maps.app.goo.gl/Kd5dAEuL75YzpK5D9 | Hydro | Eshaq Erian | 0 12 26839680 | Link
341 | Industrial Zone | ECE (Electro Cable Egypt) | 2025-12-28 | ( 18-30 KV ) MV Cables 3*240 mm2 AL/XLPE/STA/PVC (ECE) | 19757 | Approved | Hyperlink |  | attached | 8700007746 | PO.342.56.1 | Refaat Samy | 0 100 484 4488 | https://maps.app.goo.gl/wcMHoxmqB74zeAvW7 | CEGMAN | Mohamed Emad | 0 100 828 1358 | Link
342 | New Delta 2 | Stahl Crane (warehouse) | 2025-12-29 | Hoists Over Head 45 Ton & Monorails 5 Ton(Elec) & 10 Ton (Manual) | 4 | Approved | Hyperlink |  | attached |  | P.O 259-145-2 | Abd El Rahman | 0 120 464 4955 | https://maps.app.goo.gl/8EnkyG3jaxMZhLhy8 | Raouf Darwesh | Mohamed abou El Fatouh | 0 100 715 0725 | Link
343 | Al Ayat Intake - Dahshoor Booster Pump | Ateb | 2025-12-30 | Actuators for Valves | 20 | Approved | Hyperlink |  | attached |  | Contract | Yara Wageh | 0 127 665 5505 | https://maps.app.goo.gl/JpnUorai86HKNZKi7 | Enviro | Ebraheem | 0 10 04615973 | Link
344 | NACWWTP | El Sewedy (Transformers) | 2025-12-31 | El Sewedy Dry Transformers (Irrigation PS) 630 KVA 11/0.4 KV | 2 | Rejected | NO Report | TR Not ready | attached |  | PO.119.65.1 | Mostafa Shawky | 0 106 633 9761 | https://maps.app.goo.gl/ewefwJ1nYefmTEau6 | AAW | Fathy Mohamed | 0 12 73175249 | Link
345 | Sanhour | QUIPEGY | 2026-01-01 | CCTV System | As per attached | Rejected | NO Report | Difference Packing List & Approval | attached |  | PO. 317.160.2 | Mohamed Samir | 0 122 230 2713 | https://maps.app.goo.gl/7Bu2aQ4aUYu79PYV9 | Stantic | Rabee | 0 10 05851398 | Link
346 | Zone.G | Gila | 2026-01-05 | Cooling Panels for PS (01) Pumps | 5 | Approved | Hyperlink |  | attached |  | PO. 339.59.3 | Mahmoud Salem | 0 106 552 5118 | https://maps.app.goo.gl/k8p94n7Ufjz5UyVp9 | Hydro | Dr Badawy | 0 10 66866714 | Link
347 | Industrial Zone | El sewedy EGYTECH (A3 ) | 2026-01-05 | LV Cables 4*25 & 1*16 mm2 | As per attached | Approved | Hyperlink |  | attached |  | PO.342.56.5 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/CNjYGqppnuLXbMhD9 | CEGMAN | Hany Tawab Nagy | 0 12 05418255 | Link
348 | Zone.G | Pharaonic Group | 2026-01-05 | DATA & TELEPHONE & MATV | As per attached | Rejected | NO Report | Difference Packing List & Approval | attached |  | PO. 339.160.3 | Mohammed Motawea | 0 10 32072067 | https://maps.app.goo.gl/9AL8w7Zv3sMHCWk58 | Hydro | Alaa Masood | 0 12 02004447 | Link
349 | El Hammam PS(1,2) | Egylux | 2026-01-06 | Lighting Fixtures | As per attached | Approved | Hyperlink |  | attached | 8700010360 | P.O 202.76.2 | Khaled Mahmoud | 0 10 66783266 | https://maps.app.goo.gl/2Aq3diXvoZvSRRUu6 | Hydro | Fathy El Esawy | 0 10 08331443 | Link
350 | 1000 Fadan | ECE (Electro Cable Egypt) | 2026-01-11 | ( 18-30 KV ) MV Cables 3*240 mm2 AL/XLPE/STA/PVC (ECE) | 13001 | Approved | Hyperlink |  | attached | 8700007836 | PO.208.56.3 | Osama Sakr QC | 0 109 608 2226 | https://maps.app.goo.gl/CtKFX4VM4jqCMV3b8 | Khaled Kandel | Ahmed Salah | 0 110 200 2495 0 122 120 8809 | Link
351 | T.Lines (New Administration Capital) | HITEKNOFAL | 2026-01-12 | Fiber optic cables | 3800 | Approved | Hyperlink |  | attached |  | 8600123465 | Mostafa Radwan | 0 101 060 0073 | https://maps.app.goo.gl/LY2F8n8LHScU59486 | Hydro | Mahmoud Roushdy | 0 10 06578257 | Link
352 | Sinblaween | New Electric | 2026-01-13 | Spare Parts (Soft Starter & Modbus Motor Management) | As per attached | Approved | Hyperlink |  | N.A |  | PO. 114.59.10 | Mohamed Gamal | 0 10 25654245 | https://maps.app.goo.gl/Cu2g348inYDE45mV6 | Client | Mostafa Sallam | 0 10 19119669 | Link
353 | Sanhour | El sewedy EGYTECH (A1 ) | 2026-01-14 | (12-20 KV) MV Cables 3*300 mm2 AL/XLPE/STA/PVC (EGYTECH) | 2585 Meters | Approved | Hyperlink |  | attached |  | PO.317.56.3 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/6iaeqPztf8uoVZmb7 | Electricity Company | Mohamed Ali Ali | 0 112 475 9807 | Link
354 | Ain Sokhna | ICE | 2026-01-15 | Cathodic Protection ICE (Batch 02) | As per attached | Approved | Hyperlink |  | attached | 8700008973 | PO.344.299.1 | Ehab Ayman | 0 100 709 0897 | https://maps.app.goo.gl/WvHTgdAD37p2zqo17 | ECR (Engineering Consultancy & Research) | Mohamed El Saied | 0 105 024 4472 | Link
355 | Abou Oweikal | ECOPRO | 2026-01-19 | AHU Panels - Ecopro - Abo Oweikal | 4 | Approved | Hyperlink |  | attached |  | PO. 84.59.8 | Ramadan El Gamal | 0 115 559 4159 | https://maps.app.goo.gl/WweA5bpFHTrQ5VKc7 | Misr Consultant | Kenawy Shaban | 0 11 51988877 | Link
356 | El Borsa | EMAS | 2026-01-21 | RMU (3+1 LBS) / 11 KV | As per attached | Approved | Hyperlink |  | attached |  | PO.189.68.2 | Nahed Ahmed | 0 10 29974497 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | Hydro | Mahmoud Roushdy | 0 10 06578257 | Link
357 | Abou Oweikal | HAT / NAFFCO | 2026-01-26 | FM-200 & Detection System | As per attached | Approved | Hyperlink |  | attached |  | PO.84.116.3 | Ahmed Abd El Nasser | 0 12 79242003 | https://maps.app.goo.gl/jR6bR7soBvyDFaKE9 | Misr Consultant | Mohamed Abbas | 0 11 50575814 | Link
358 | NACWWTP | El Sewedy (Transformers) | 2026-01-28 | El Sewedy Dry Transformers (Irrigation PS) 630 KVA 11/0.4 KV | 2 | Approved | Hyperlink |  | attached |  | PO.119.65.1 | Mostafa Shawky | 0 106 633 9761 | https://maps.app.goo.gl/ewefwJ1nYefmTEau6 | AAW | Fathy Mohamed | 0 12 73175249 | Link
359 | 6 October tretment Plant | Novovent Fans | 2026-02-02 | Exhaust Fans | 3 | Approved with comments | Hyperlink | Need approval TGT/4-900/ 6/12 BC | attached |  | P.O 159.130.5 | Ahmed Salah | 0 122 299 8517 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | Enviro | Gamal Badeir | 0 11 17397557 | Link
360 | Zone.G | Pharaonic Group | 2026-02-04 | DATA & TELEPHONE & MATV | As per attached | Approved | Hyperlink |  | attached |  | PO. 339.160.3 | Mohammed Motawea | 0 10 32072067 | https://maps.app.goo.gl/9AL8w7Zv3sMHCWk58 | Hydro | Mohamed abd El Mohaymen | 0 11 13233463 | Link
361 | Zone.G | MAM for Engineering Industries & Electrical Supplies | 2026-02-09 | DP - MVSWGR / DP - UPS -VFD | 2 | Approved | HyperLink | [6 empty] | https://maps.app.goo.gl/zrMojfznkPNkjX9Z7 | Hydro | Mohamed abd El Mohaymen | 0 11 13233463 | Link
362 | Meet El Amel | ESC | 2025-02-15 | FAT Test Pump Meet El Amel Model :- ARS 100 A-35 U/30 | 1 | Approved | Hyperlink |  | attached |  | N.A | Mohamed abd Elnasser | 0 128 781 6955 | https://maps.app.goo.gl/uVZkarCAsM8bscHv9 | N.A | N.A | N.A | N.A
363 | Toshka Zone.S | MISR Engineering Work Cranes | 2026-02-16 | Hoists 5 Ton | As per attached | Approved | Hyperlink |  | attached |  | PO 307.145.3 | Radwan | 0 11 27238589 | https://maps.app.goo.gl/y1XHMuqpnGRJVBAR9 | Cairo University | Mohamed Sofar | 0 11 45117582 | Link
364 | Tahta treatment Plant | MISR Engineering Work Cranes | 2026-02-16 | Hoists 5 Ton | As per attached | Approved | Hyperlink |  | attached |  | PO 192.145.3 | Radwan | 0 11 27238589 | https://maps.app.goo.gl/y1XHMuqpnGRJVBAR9 | SABBOUR | N.A | N.A | Link
365 | Tahta treatment Plant | UIC (El Sewedy Special Cables) | 2026-02-17 | Remaining Control Cables | As per attached | Approved | Hyperlink |  | attached | 8700010397 8700010237 | PO. 192.56.4.sup.01 PO. 192.56.5.adden.01 | Ahmed Samir Abdulaziz | 0 122 916 2071 | https://maps.app.goo.gl/8RPcwRcxHnFdDaF39 | SABBOUR | N.A | N.A | Link
366 | Tahta treatment Plant | Nova | 2026-02-17 | Gear Boxes | 12 | Approved | Hyperlink |  | attached | 8700011211 | PO.192.296.5 | Aref Helmy | 0 10 80053531 | https://maps.app.goo.gl/iZyEhsVtuZ5mfLkH8 | SABBOUR | N.A | N.A | Link
367 | Sanhour | QUIPEGY | 2026-02-17 | CCTV System | As per attached | Approved | Hyperlink |  | attached |  | PO. 317.160.2 | Mohamed Samir | 0 122 230 2713 | https://maps.app.goo.gl/7Bu2aQ4aUYu79PYV9 | Stantic | Rabee | 0 10 05851398 | Link
368 | Intake Mostakbal Misr | BICC | 2026-02-19 | LV Wires & Cables | As per attached | Approved | Hyperlink |  | attached |  | PO 223.56.7 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | HYDRO | El Nagar | 0 10 98678092 | N.A
369 | NACWWTP | Giza Cables | 2026-02-23 | LV Cables(Street LV Cables) (New Administration Capital Waste Water Tratment Plant) | As per attached | Approved | hyperlink |  | attached |  | PO 119.56.5 | Hassan Ali | 0 109 711 8883 | https://maps.app.goo.gl/YiRTzz6HfLJYb5vX6 | AAW | Fathy Mohamed | 0 12 73175249 | Link
370 | 1000 Fadan | ECE (Electro Cable Egypt) | 2026-03-02 | LV Cables 3*150+70 mm2 at ECE (Electro Cable Egypt) | 563 Meter | Approved | HyperLink |  | attached | 8700007836 | PO.208.56.3 | Osama Sakr QC | 0 109 608 2226 | https://maps.app.goo.gl/BBSFDZ786VzQgQG16 | Khaled Kandel | Ahmed Salah | 0 110 200 2495 0 122 120 8809 | Link
371 | El Hammam PS(1,2) | Infinity | 2026-03-04 | Fire Pumps (Elec & Jockey & Diesel) synchro flo | As per attached | Approved | Hyperlink |  | attached |  | P.O 202.104.2 | Mohamed Nadeem | 0 10 17717723 | https://maps.app.goo.gl/Y3Wwd1UTx2ezXkmp8 | HYDRO | Ramy Maher | 0 12 71505297 | Link
372 | Industrial Zone Waste water Plant | BICC | 2026-03-04 | LV Wires (3 & 4 ) mm2 | As per attached | Approved | N.A |  | attached |  | PO. 342.56.6 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | CEGMAN | Hany Tawab Nagy | 0 12 05418255 | Link
373 | Tahta treatment Plant | SPEC | 2026-03-12 | switches & servers | As per attached | Approved | Hyperlink |  | attached | 8700011067 | PO.192.160.2 | Karim Safwat | 0 101 181 9701 | https://maps.app.goo.gl/S6pKZXFUvo4VUzZi6 | SABBOUR | N.A | N.A | Link
374 | Industrial Zone Waste water Plant | Zaki El Sewedy | 2026-03-15 | RMU (3+1 LBS) / 22 KV | 1 | Approved | Hyperlink |  | attached |  | PO.342.68.3 | Abnoub | 0 10 10035226 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | CEGMAN | Hany Tawab Nagy | 0 12 05418255 | Link
375 | Meet El Amel | SinaMix | 2026-03-16 | PLC For Blowers | As per attached | Approved | Hyperlink |  | N.A |  | PO. 157.107.1 | Amr Hafez | 0 101 116 3510 | https://maps.app.goo.gl/1PhG8aFcF9djKBmB6 | Water Comapany | Mostafa Sallam | 0 10 19119669 | Link
376 | Al Ayat Intake - Dahshoor Booster Pump | BICC | 2026-03-17 | LV Wires | As per attached | Approved | Hyperlink |  | attached |  | PO. 329.56.1 | Eid Hanafy | 0 100 123 5055 | https://maps.app.goo.gl/LPS8YS4F62D6DKVm9 | Enviro | Youssef El Saeedy | 0 10 61598033 | Link
377 | Zone.G | ECAI | 2026-03-29 | Actuators | 7 | Approved | Hyperlink |  | attached |  | PO 339.296.4 | El Sayed Mesbah | 0 100 101 2371 | https://maps.app.goo.gl/bbPHTUgU7AEBVXZw6 | HYDRO | Mohamed abd El Mohaymen | 0 11 13233463 | Link
378 | Zone.G | Schenider | 2026-03-31 | LV Sub Service Panel | 1 | Approved | Hyperlink |  | attached | 8700009326 | PO.259.68.1 | Ahmed Fawzy | 0 127 905 9616 | https://maps.app.goo.gl/k6MPEXBdco6r31nPA | Hydro | Hassan Saber | 0 10 33024669 | Link
379 | New Delta 2 | Aucom | 2026-04-02 | Online FAT Soft Starter | 5 | Approved | Hyperlink |  | attached |  | PO. 259.168.4 | Online | Online | OnLine @ Germany | Raouf Darwesh | N.A | N.A | Link
380 | Ain Sokhna | ICE | 2026-04-08 | Cathodic Protection ICE (Batch 03) | As per attached | Approved | Hper Link |  | attached | 8700008973 | PO.344.299.1 | Ehab Ayman | 0 100 709 0897 | https://maps.app.goo.gl/WvHTgdAD37p2zqo17 | ECR (Engineering Consultancy & Research) | Mohamed El Saied | 0 105 024 4472 | Link
381 | El Hammam PS(1,2) | schenider | 2026-04-15 | Marshalling Panels - LCP - Main Pumps | As per attached | Approved with comments | Hyperlink |  | attached |  | PO. 202.107.4 Adden.02 | Eslam Emad | 0 101 649 4837 | https://maps.app.goo.gl/W4szEG4tZs6pe8Gy5 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
382 | Maghagha JV | TEPECO | 2026-04-19 | LV ATS Auxiliry panel | 1 | Approved | Hyperlink |  | attached |  | PO 218.59.8 | Mohamed Ebrahim | 0 11 44077333 | https://maps.app.goo.gl/7vwVC37gUGxr2VeC6 | N.A | N.A | N.A | Link
383 | Industrial Zone | Capital Guard | 2026-04-20 | Weighning Devices for Fire fighting system | As per attached | Approved with comments | Hyperlink | Need Approval | attached |  | 342.116.2 | Ragaa | 0 12 79162000 | https://maps.app.goo.gl/2aJf5Pmbahgzvn1k6 | N.A | N.A | N.A | Link
384 | Industrial Zone | Zaki El Sewedy | 2026-04-22 | Kiosk 50 KV 22/0.4 KV for Kiosk (Zaki Elsewedy ) | 4 | Rejected | NO Report |  | attached |  | PO.342.279.1 | Abnoub | 0 10 10035226 | https://maps.app.goo.gl/7DhUs2oR3frXD31XA | CEGMAN | Hany Tawab Nagy | 0 12 05418255 | Link
385 | New Delta 2 | Stahl Crane (warehouse) | 2026-04-26 | Hoist Gantry Crane | 1 | Approved | Hyperlink |  | attached |  | P.O 259-145-3 | Tarek Sakr | 0 109 868 6342 | https://maps.app.goo.gl/8EnkyG3jaxMZhLhy8 | Raouf Darwesh | Mohamed Emaraa | 0 11 2 886 2383 | Link
386 | Lines October WTP | Brilliant | 2026-04-27 | Water Hammer - Brilliant - | 2 | Rejected | NO Report |  | attached |  | Contract Water Hammer | Mostafa Hassan | 0 | https://maps.app.goo.gl/9KLqstjgDJvm8KXW6 | المركز القومي للبحوث | N.A | N.A | Link
387 | Al Ayat Intake - Dahshoor Booster Pump | AL Andulus | 2026-04-28 | water hammer | 4 | Approved | Hyperlink |  | attached |  | Contract Water Hammer | Soad Shawky | 0 12 28334851 | https://maps.app.goo.gl/LuxEcf3spAizFCh38 | Enviro | Ebraheem | 0 10 04615973 | Link
388 | El Hammam PS(1,2) | Gila | 2026-05-11 | Cooling & Gear Box Panels | 24 | Approved with comments | Hyperlink |  | attached |  | PO. 202.59.3 | Mahmoud Salem | 0 106 552 5118 | https://maps.app.goo.gl/k8p94n7Ufjz5UyVp9 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
389 | Tahta treatment Plant | lectro Power - El Habashy | 2026-05-19 | BusWay 3200 A WTP for Treatment Plant | As per attached | Approved | Hyperlink |  | attached |  | Contract 192-58-01 | Moustafa | 0 110 160 0909 | https://maps.app.goo.gl/i7gCszWecJs1Cn6bA | SABBOUR | N.A | N.A | Link
390 | Maghagha JV | CPT Cusomized Power Technology | 2026-05-20 | Generators 225 KVA (El Sheikh Zyad ) | 1 | Approved | Hyperlink |  | attached | 9600001065 | PO.218.66.2 | Beshoy | 0 11 26499223 | https://maps.app.goo.gl/WH9s5Wk1LktYJeWF7 | N.A | N.A | N.A | Link
391 | Sanhour | El sewedy EGYTECH (A1 ) | 2026-05-24 | (12-20 KV) MV Cables 3*300 mm2 AL/XLPE/STA/PVC (EGYTECH) | 2831 | Approved | Hyperlink |  | attached |  | PO. 317.56.4 | Mohmed Shahat | 0 100 8482612 | https://maps.app.goo.gl/6iaeqPztf8uoVZmb7 | Electricity Company | Mohamed Ali Ali | 0 112 475 9807 | Link
392 | Maghagha JV | SEGA.M | 2026-11-05 | DB -TR Maghagha JV Projecrt | 1 | Approved | Hyperlink |  | attached |  | PO218.59.10 adden | Hany Henry | 0 100 216 2226 | https://maps.app.goo.gl/6TwbXifJWZyDKM456 | N.A | N.A | N.A | N.A
393 | El Borsa | El Sewedy (Transformers) | 2026-06-03 | Dry Transformers 200 KVA 22/0.4 KV for Kiosk 200KVA | 1 | Approved | Hyperlink |  | attached |  | PO.189.68.2 | Nahed Ahmed | 0 10 29974497 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | Hydro | Mahmoud Roushdy | 0 10 06578257 | Link
394 | Al Ayat Intake - Dahshoor Booster | GEMKA | 2026-06-09 | Penstocks | As per attached |  |  |  | attached |  | PO 329.296.1 | Mohamed assad | 0 10 06757564 | https://maps.app.goo.gl/7VDKweb4FsGeQeim6 | Enviro | Ebraheem | 0 10 04615973 | Link
395 | NACWWTP | GEMKA | 2026-06-09 | Penstocks & Actuators | As per attached |  |  |  | attached |  | P.O 119-296-2 | Mohamed assad | 0 10 06757564 | https://maps.app.goo.gl/7VDKweb4FsGeQeim6 | AAW | Fathy Mohamed | 0 12 73175249 | Link
396 | El Hammam PS(1,2) | Schneider (Tricom) | 2026-06-10 | RTU Siphone & Regulator | 2 |  |  |  | attached |  | PO.202.107.3 | Omar Assem | 0 127 898 6334 | https://maps.app.goo.gl/aHKospfVv7apcdWs8 | Hydro | Fathy El Esawy | 0 100 833 1443 | Link
397 | Zone.G | Gila | 2026-06-14 | RTU Feeder LV Panels | 19 |  |  |  | attached |  | PO 339.59.4 | Mahmoud Salem | 0 106 552 5118 | https://maps.app.goo.gl/k8p94n7Ufjz5UyVp9 | Hydro | Hassan Saber | 0 103 302 4669 | Link
398 | 1000 Fadan | EMAS | Waiting | MV SWGR | 1 |  |  |  | attached |  | P.O 208.68.2 | Nahed Ahmed | 0 10 29974497 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | Khaled Kandel | Ahmed Salah | 0 110 200 2495 0 122 120 8809
399 | Al Ayat Intake - Dahshoor Booster | EMAS | Waiting | RMU | 4 |  |  |  | attached |  | PO. 329.68.1 | Nahed Ahmed | 0 10 29974497 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | Enviro | Youssef El Saeedy | 0 10 61598033
400 | North Sinai (Gefgafa) | Novovent Fans | 2026-06-17 | Exhaust & Supply fans for Gefgafa Project PS 12 & 13 | as per attached |  |  |  | attached | 8700007464 | PO.308.130.1 | Ahmed Salah | 0 122 299 8517 | https://maps.app.goo.gl/Cg3Q5ag62DUyDirw7 | Raouf Darwesh | Mohamed abou El Fatouh | 0 100 715 0725
401 | El Borsa | EMAS | Waiting | Kiosks 200 KVA | 1 |  |  |  | attached |  | PO.189.68.2 | Nahed Ahmed | 0 10 29974497 | https://maps.app.goo.gl/aTywsNbGqQ5jpXdy9 | Hydro | Mahmoud Roushdy | 0 10 06578257

## Safaga
15
Serial | Project | Factory & Supplier | Date | Desc. | Quantity | Status | Report | Location | Reference | po/sap | PO no
1 | Safaga Port | El Sewedy | 2025-10-01 | LV Earth Cables | As Per attached | Approved | Link | 10th of Ramadan City
2 | Safaga Port | El Sewedy | 2025-10-12 | LV Cables | As Per attached | Approved | Link | 10th of Ramadan City
3 | Safaga Port | El Sewedy | 2025-10-28 | LV Cables | As Per attached | Approved | Link | 10th of Ramadan City
4 | Safaga Port | El Sewedy | 2025-11-10 | LV Cables | As Per attached | Approved | Link | 10th of Ramadan City
5 | Safaga Port | INDE | 2025-12-01 | Generator Accessories ( Daily Tank, Spring Isolators, Exhaust System, ..... ) | As Per attached | Approved | Link | 6th of October City
6 | Safaga Port | MK | 2025-12-02 | FM 200 | As Per attached | Approved | Link | Badr City
7 | Safaga Port | El Sewedy Transformers | 2025-12-03 | Dry Transformers 1000 & 1500 KVA (11/0.4 KV) | 2 | Approved | Link | 10th of Ramadan City
8 | Safaga Port | El Babtin | 2025-12-04 | High Mast | As Per attached | Approved | Link | 6th of October City
9 | Safaga Port | Gazelle Trade | 2025-12-07 | Seamless Pipes, Grooved and Threaded Pipes | As Per attached | Approved | Link | New Cairo
10 | Safaga Port | El Sewedy | 2025-12-08 | MV Cables | As Per attached | Approved | Link | 10th of Ramadan City
11 | Safaga Port | Novovent | 2025-12-09 | Exhaust & Supply Fans | As Per attached | Approved | Link | Borg El Arab
12 | Safaga Port | Unitech | 2025-12-10 | Cable Tray | As Per attached | Approved | Link | 6th of October City
13 | Safaga Port | Rockal | 2025-12-11 | Duct Insulation (Fiber Glass, Glass Wool, ...) | As Per attached | Approved | Link | Obour City
14 | Safaga Port | El Sewedy | 2025-12-16 | LV Cables | As Per attached | Approved | Link | 10th of Ramadan City
15 | Safaga Port | El Sewedy | 2025-12-17 | LV Cables | As Per attached | Approved | Link | 10th of Ramadan City